## Management View
Enterprise AI Audit Recommendation Engine -- Sprint Plan
Project: JNJ TPI Due Diligence ¦ Platform: Databricks (Unity Catalog) ¦ End Date: 28-Feb-2027 ¦ Total Sprints: 15
Sprint # | Sprint Name | Goal | Start Date | End Date | Duration | Tasks | Phase
Sprint 1 | Policy & Use Case Finalization | Understand HCBI and local policies, define red flag criteria, finalize 48 scope areas and audit use cases | 01-May-2026 | 28-Jun-2026 | 8 weeks | 7 | Policy & Use Case
Sprint 2 | MVP Build -- Full Pipeline for TPI Due Diligence | Build the complete end-to-end pipeline for one scope (TPI Due Diligence): all ingestion, all agents, services, transactional layer and output | 29-Jun-2026 | 02-Sep-2026 | 9 weeks | 32 | MVP Full Build
Sprint 3 | Simulation Validation & MVP Hardening | Validate MVP simulation results for TPI Due Diligence, fix pipeline bugs, refine prompts and retrieval quality | 03-Sep-2026 | 24-Sep-2026 | 3 weeks | 8 | Validation & Hardening
Sprint 4 | Scope Expansion -- Onboard Scope Areas 2-4 | Ingest policy documents and supporting evidence for scope areas 2 to 4; run and validate simulation | 25-Sep-2026 | 08-Oct-2026 | 2 weeks | 6 | Scope Expansion (2-4)
Sprint 5 | Scope Expansion -- Onboard Scope Areas 5-8 | Ingest policy documents and supporting evidence for scope areas 5 to 8; run and validate simulation | 09-Oct-2026 | 22-Oct-2026 | 2 weeks | 6 | Scope Expansion (5-8)
Sprint 6 | Scope Expansion -- Onboard Scope Areas 9-12 | Ingest policy documents and supporting evidence for scope areas 9 to 12; run and validate simulation | 23-Oct-2026 | 05-Nov-2026 | 2 weeks | 6 | Scope Expansion (9-12)
Sprint 7 | Scope Expansion -- Onboard Scope Areas 13-18 | Ingest policy documents and supporting evidence for scope areas 13 to 18; run and validate simulation | 06-Nov-2026 | 19-Nov-2026 | 2 weeks | 6 | Scope Expansion (13-18)
Sprint 8 | Scope Expansion -- Onboard Scope Areas 19-24 | Ingest policy documents and supporting evidence for scope areas 19 to 24; run and validate simulation | 20-Nov-2026 | 03-Dec-2026 | 2 weeks | 6 | Scope Expansion (19-24)
Sprint 9 | Scope Expansion -- Onboard Scope Areas 25-36 | Ingest policy documents and supporting evidence for scope areas 25 to 36; run and validate simulation | 04-Dec-2026 | 17-Dec-2026 | 2 weeks | 6 | Scope Expansion (25-36)
Sprint 10 | Scope Completion -- All 48 Scope Areas | Ingest documents for remaining scope areas 37-48; achieve full 48-scope coverage and run complete simulation | 18-Dec-2026 | 31-Dec-2026 | 2 weeks | 6 | Scope Completion (37-48)
Sprint 11 | Dual Output Design & Ishita Layout Integration | Build and finalize Output 1 (detailed per question) and Output 2 (top scope areas summary); align with Ishita output layout | 01-Jan-2027 | 14-Jan-2027 | 2 weeks | 6 | Output Design
Sprint 12 | Full Simulation & Quality Assurance | Run complete simulation across all 48 scope areas with transactional analysis; comprehensive end-to-end QA | 15-Jan-2027 | 28-Jan-2027 | 2 weeks | 7 | Full Simulation & QA
Sprint 13 | SME Validation & Feedback Integration | SME review of AI findings, incorporate feedback into prompts and guardrails, business UAT and sign-off | 29-Jan-2027 | 11-Feb-2027 | 2 weeks | 6 | SME Validation
Sprint 14 | Stabilization, UAT & Production Preparation | Final prompt tuning, performance hardening, security review and production environment setup on Databricks | 12-Feb-2027 | 19-Feb-2027 | 1 weeks | 6 | Stabilization & UAT
Sprint 15 | Production Rollout & Project Handover | Deploy to production, set up monitoring and alerting, complete knowledge transfer and project closure | 20-Feb-2027 | 28-Feb-2027 | 1 weeks | 5 | Production Rollout

## Gantt Chart
Gantt Chart -- Enterprise AI Audit Recommendation Engine
Task Ref | Category | Task Description | Start Date | End Date | 04/05 | 11/05 | 18/05 | 25/05 | 01/06 | 08/06 | 15/06 | 22/06 | 29/06 | 06/07 | 13/07 | 20/07 | 27/07 | 03/08 | 10/08 | 17/08 | 24/08 | 31/08 | 07/09 | 14/09 | 21/09 | 28/09 | 05/10 | 12/10 | 19/10 | 26/10 | 02/11 | 09/11 | 16/11 | 23/11 | 30/11 | 07/12 | 14/12 | 21/12 | 28/12 | 04/01 | 11/01 | 18/01 | 25/01 | 01/02 | 08/02 | 15/02 | 22/02
Sprint 1: Policy & Use Case Finalization -- 01 May 2026 to 28 Jun 2026
1.1 | Policy & Use Case | Review HCBI Global Policy (TV-POL-02257_v3.0.pdf) -- 115 pages, image-based PDF | 01-May-2026 | 08-May-2026
1.2 | Policy & Use Case | Review all 7 Local Policies TPI (TPEC, Red Flag, SOP, BGS and associated documents) | 09-May-2026 | 16-May-2026
1.3 | Policy & Use Case | Study Planning Questionnaire and IDR Questionnaire -- column structure and response formats | 17-May-2026 | 24-May-2026
1.4 | Policy & Use Case | Define red flag criteria and risk assessment decision framework | 25-May-2026 | 02-Jun-2026
1.5 | Policy & Use Case | Identify use cases -- risk types, compliance check scenarios, conflict detection scenarios | 03-Jun-2026 | 10-Jun-2026
1.6 | Policy & Use Case | Finalize 48 scope areas; confirm TPI Due Diligence as the active MVP scope | 11-Jun-2026 | 18-Jun-2026
1.7 | Documentation | Create BRD, Architecture and Flow doc, AI Auditor Documentation and Sprint Plan | 19-Jun-2026 | 27-Jun-2026
Sprint 2: MVP Build -- Full Pipeline for TPI Due Diligence -- 29 Jun 2026 to 02 Sep 2026
2.1 | Data Prep | Set up config.py, settings.py and .env structure with all Azure OpenAI and Databricks variables | 29-Jun-2026 | 30-Jun-2026
2.2 | Data Prep | Build schemas/state.py -- Pydantic models: QuestionRow, AuditState, RiskOutput, TransactionalQueryResult, ConflictFlag | 01-Jul-2026 | 02-Jul-2026
2.3 | Data Prep | Set up azure_openai.py (GPT-5 via JNJ gateway) and embedder.py (text-embedding-3-small) | 03-Jul-2026 | 04-Jul-2026
2.4 | Data Prep | Build pdf_extractor.py -- pdfplumber + PyMuPDF + Azure Document Intelligence for image-based PDFs | 05-Jul-2026 | 06-Jul-2026
2.5 | Data Prep | Build excel_extractor.py (pandas + openpyxl) and word_extractor.py (python-docx) | 07-Jul-2026 | 08-Jul-2026
2.6 | Data Prep | Build ppt_extractor.py (python-pptx + OCR) and html_extractor.py (BeautifulSoup) | 09-Jul-2026 | 10-Jul-2026
2.7 | Data Prep | Build email_extractor.py (extract-msg) with recursive nested attachment extraction | 11-Jul-2026 | 12-Jul-2026
2.8 | Data Prep | Build document_loader.py -- universal format router with recursive directory walk for all volume paths | 13-Jul-2026 | 14-Jul-2026
2.9 | Data Prep | Build chunker.py -- section-aware chunking (800 tokens max, 1-paragraph overlap) | 15-Jul-2026 | 16-Jul-2026
2.10 | Data Prep | Process HCBI Global Policy PDF (image-based, 115 pages) via Azure Document Intelligence + OCR | 17-Jul-2026 | 18-Jul-2026
2.11 | Data Prep | Process all 7 Local Policies TPI documents (PDFs and .doc) via document loader | 19-Jul-2026 | 20-Jul-2026
2.12 | Data Prep | Process Master Audit Skills PDFs (4 modules) -- load as system context into Delta table | 21-Jul-2026 | 22-Jul-2026
2.13 | Data Prep | Process all Supporting Documents from Databricks Volume (recursive directory walk, all formats) | 23-Jul-2026 | 24-Jul-2026
2.14 | Data Prep | Build vector_store.py -- Databricks Vector Search client (create, upsert, query) | 25-Jul-2026 | 26-Jul-2026
2.15 | Data Prep | Create and populate hcbi_index with HCBI Global Policy chunks (text-embedding-3-small, 1536 dims) | 27-Jul-2026 | 28-Jul-2026
2.16 | Data Prep | Create and populate due_diligence_index with TPI Local Policy chunks | 29-Jul-2026 | 30-Jul-2026
2.17 | Data Prep | Create and populate supporting_docs_index with Supporting Document chunks | 31-Jul-2026 | 01-Aug-2026
2.18 | Data Prep | Load 3 transactional data files into Delta tables: Payments, Credit Memo, Revenue (TPI scope) | 02-Aug-2026 | 03-Aug-2026
2.19 | LLM Dev | Build hcbi_retrieval_tool.py, policy_retrieval_tool.py, evidence_retrieval_tool.py | 04-Aug-2026 | 05-Aug-2026
2.20 | LLM Dev | Build conflict_detector.py -- InMemoryStore cross-row semantic similarity (threshold 0.90) | 06-Aug-2026 | 07-Aug-2026
2.21 | LLM Dev | Build policy_knowledge_agent.py -- queries hcbi_index and due_diligence_index in parallel | 08-Aug-2026 | 09-Aug-2026
2.22 | LLM Dev | Build evidence_assessment_agent.py -- semantic search + targeted retrieval by cited document name | 10-Aug-2026 | 11-Aug-2026
2.23 | LLM Dev | Build context_aggregator.py -- source hierarchy ranking (HCBI > Local Policy > Supporting Docs) | 12-Aug-2026 | 13-Aug-2026
2.24 | LLM Dev | Build scope_mapper.py -- cosine similarity against 48 pre-computed scope embeddings | 14-Aug-2026 | 15-Aug-2026
2.25 | LLM Dev | Build risk_evaluation_agent.py -- GPT-5, compliance gap identification, transactional intent detection | 16-Aug-2026 | 17-Aug-2026
2.26 | LLM Dev | Build risk_analyzer_agent.py -- GPT-5, scope assignment, risk scores, final 10-point validation | 18-Aug-2026 | 19-Aug-2026
2.27 | LLM Dev | Build transactional_data_agent.py -- NL-to-SQL, conditional trigger, TPI Due Diligence scope filter | 20-Aug-2026 | 21-Aug-2026
2.28 | LLM Dev | Build questionnaire_repo.py, output_repo.py, scope_repo.py (Delta table read/write repositories) | 22-Aug-2026 | 23-Aug-2026
2.29 | LLM Dev | Define LangGraph StateGraph in main.py -- wire all 5 agents with asyncio.gather and conditional TDA edge | 24-Aug-2026 | 25-Aug-2026
2.30 | LLM Dev | Build output_writer.py -- Part A original columns + Part B AI columns, dual output structure | 26-Aug-2026 | 27-Aug-2026
2.31 | LLM Dev | End-to-end simulation: run full pipeline on TPI Due Diligence (Planning + IDR questionnaires) | 28-Aug-2026 | 29-Aug-2026
2.32 | LLM Dev | Validate simulation output -- risk classifications, scope assignments, evidence citations, conflict flags | 30-Aug-2026 | 01-Sep-2026
Sprint 3: Simulation Validation & MVP Hardening -- 03 Sep 2026 to 24 Sep 2026
3.1 | LLM Dev | Review all risk classifications from MVP simulation; compare against expected audit outcomes | 03-Sep-2026 | 04-Sep-2026
3.2 | LLM Dev | Assess scope mapping accuracy across all TPI Due Diligence questions | 05-Sep-2026 | 07-Sep-2026
3.3 | LLM Dev | Test edge cases -- blank responses, generic responses, conflicting cross-row responses | 08-Sep-2026 | 09-Sep-2026
3.4 | LLM Dev | Tune retrieval parameters -- top-k, chunk size, similarity thresholds based on simulation results | 10-Sep-2026 | 12-Sep-2026
3.5 | LLM Dev | Refine prompts for Risk Evaluation Agent and Risk Analyzer Agent based on failure cases | 13-Sep-2026 | 15-Sep-2026
3.6 | LLM Dev | Fix pipeline bugs and output schema issues identified in MVP simulation run | 16-Sep-2026 | 17-Sep-2026
3.7 | LLM Dev | Validate conflict detection logic -- review all flagged cross-row conflicts for accuracy | 18-Sep-2026 | 20-Sep-2026
3.8 | Data Prep | Performance testing -- async parallel retrieval benchmarking; identify and fix bottlenecks | 21-Sep-2026 | 23-Sep-2026
Sprint 4: Scope Expansion -- Onboard Scope Areas 2-4 -- 25 Sep 2026 to 08 Oct 2026
4.1 | Policy & Use Case | Identify and collate local policy documents and supporting evidence for scope areas 2-4 | 25-Sep-2026 | 26-Sep-2026
4.2 | Data Prep | Ingest local policy documents for scope areas 2-4 (all formats, recursive volume walk) | 27-Sep-2026 | 28-Sep-2026
4.3 | Data Prep | Update due_diligence_index with policy chunks for scope areas 2-4 | 29-Sep-2026 | 30-Sep-2026
4.4 | Data Prep | Ingest and index supporting documents for scope areas 2-4 into supporting_docs_index | 01-Oct-2026 | 02-Oct-2026
4.5 | LLM Dev | Run simulation on questionnaire questions relevant to scope areas 2-4 | 03-Oct-2026 | 04-Oct-2026
4.6 | LLM Dev | Validate output quality -- risk rationale, evidence classification, scope confidence for areas 2-4 | 05-Oct-2026 | 07-Oct-2026
Sprint 5: Scope Expansion -- Onboard Scope Areas 5-8 -- 09 Oct 2026 to 22 Oct 2026
5.1 | Policy & Use Case | Identify and collate local policy documents and supporting evidence for scope areas 5-8 | 09-Oct-2026 | 10-Oct-2026
5.2 | Data Prep | Ingest local policy documents for scope areas 5-8 (all formats, recursive volume walk) | 11-Oct-2026 | 12-Oct-2026
5.3 | Data Prep | Update due_diligence_index with policy chunks for scope areas 5-8 | 13-Oct-2026 | 14-Oct-2026
5.4 | Data Prep | Ingest and index supporting documents for scope areas 5-8 into supporting_docs_index | 15-Oct-2026 | 16-Oct-2026
5.5 | LLM Dev | Run simulation on questionnaire questions relevant to scope areas 5-8 | 17-Oct-2026 | 18-Oct-2026
5.6 | LLM Dev | Validate output quality -- risk rationale, evidence classification, scope confidence for areas 5-8 | 19-Oct-2026 | 21-Oct-2026
Sprint 6: Scope Expansion -- Onboard Scope Areas 9-12 -- 23 Oct 2026 to 05 Nov 2026
6.1 | Policy & Use Case | Identify and collate local policy documents and supporting evidence for scope areas 9-12 | 23-Oct-2026 | 24-Oct-2026
6.2 | Data Prep | Ingest local policy documents for scope areas 9-12 (all formats, recursive volume walk) | 25-Oct-2026 | 26-Oct-2026
6.3 | Data Prep | Update due_diligence_index with policy chunks for scope areas 9-12 | 27-Oct-2026 | 28-Oct-2026
6.4 | Data Prep | Ingest and index supporting documents for scope areas 9-12 into supporting_docs_index | 29-Oct-2026 | 30-Oct-2026
6.5 | LLM Dev | Run simulation on questionnaire questions relevant to scope areas 9-12 | 31-Oct-2026 | 01-Nov-2026
6.6 | LLM Dev | Validate output quality and fix scope mapping issues for areas 9-12 | 02-Nov-2026 | 04-Nov-2026
Sprint 7: Scope Expansion -- Onboard Scope Areas 13-18 -- 06 Nov 2026 to 19 Nov 2026
7.1 | Policy & Use Case | Identify and collate local policy documents and supporting evidence for scope areas 13-18 | 06-Nov-2026 | 07-Nov-2026
7.2 | Data Prep | Ingest local policy documents for scope areas 13-18 (all formats, recursive volume walk) | 08-Nov-2026 | 09-Nov-2026
7.3 | Data Prep | Update due_diligence_index with policy chunks for scope areas 13-18 | 10-Nov-2026 | 11-Nov-2026
7.4 | Data Prep | Ingest and index supporting documents for scope areas 13-18 into supporting_docs_index | 12-Nov-2026 | 13-Nov-2026
7.5 | LLM Dev | Run simulation on questionnaire questions relevant to scope areas 13-18 | 14-Nov-2026 | 15-Nov-2026
7.6 | LLM Dev | Validate output quality and fix scope mapping issues for areas 13-18 | 16-Nov-2026 | 18-Nov-2026
Sprint 8: Scope Expansion -- Onboard Scope Areas 19-24 -- 20 Nov 2026 to 03 Dec 2026
8.1 | Policy & Use Case | Identify and collate local policy documents and supporting evidence for scope areas 19-24 | 20-Nov-2026 | 21-Nov-2026
8.2 | Data Prep | Ingest local policy documents for scope areas 19-24 (all formats, recursive volume walk) | 22-Nov-2026 | 23-Nov-2026
8.3 | Data Prep | Update due_diligence_index with policy chunks for scope areas 19-24 | 24-Nov-2026 | 25-Nov-2026
8.4 | Data Prep | Ingest and index supporting documents for scope areas 19-24 into supporting_docs_index | 26-Nov-2026 | 27-Nov-2026
8.5 | LLM Dev | Run simulation on questionnaire questions relevant to scope areas 19-24 | 28-Nov-2026 | 29-Nov-2026
8.6 | LLM Dev | Validate output quality and refine prompts for scope areas 19-24 | 30-Nov-2026 | 02-Dec-2026
Sprint 9: Scope Expansion -- Onboard Scope Areas 25-36 -- 04 Dec 2026 to 17 Dec 2026
9.1 | Policy & Use Case | Identify and collate local policy documents and supporting evidence for scope areas 25-36 | 04-Dec-2026 | 05-Dec-2026
9.2 | Data Prep | Ingest local policy documents for scope areas 25-36 (all formats, recursive volume walk) | 06-Dec-2026 | 07-Dec-2026
9.3 | Data Prep | Update due_diligence_index with policy chunks for scope areas 25-36 | 08-Dec-2026 | 09-Dec-2026
9.4 | Data Prep | Ingest and index supporting documents for scope areas 25-36 into supporting_docs_index | 10-Dec-2026 | 11-Dec-2026
9.5 | LLM Dev | Run simulation on questionnaire questions relevant to scope areas 25-36 | 12-Dec-2026 | 13-Dec-2026
9.6 | LLM Dev | Validate output quality and fix scope mapping issues for areas 25-36 | 14-Dec-2026 | 16-Dec-2026
Sprint 10: Scope Completion -- All 48 Scope Areas -- 18 Dec 2026 to 31 Dec 2026
10.1 | Policy & Use Case | Identify and collate local policy documents and supporting evidence for scope areas 37-48 | 18-Dec-2026 | 19-Dec-2026
10.2 | Data Prep | Ingest local policy documents for scope areas 37-48 (all formats, recursive volume walk) | 20-Dec-2026 | 21-Dec-2026
10.3 | Data Prep | Update due_diligence_index and supporting_docs_index for scope areas 37-48 | 22-Dec-2026 | 23-Dec-2026
10.4 | LLM Dev | Run full simulation across all 48 scope areas (Planning + IDR questionnaires) | 24-Dec-2026 | 25-Dec-2026
10.5 | LLM Dev | Validate coverage -- confirm all questions are correctly scope-mapped across all 48 areas | 26-Dec-2026 | 27-Dec-2026
10.6 | LLM Dev | Cross-scope consistency check -- verify consistent risk classification logic across all 48 scopes | 28-Dec-2026 | 30-Dec-2026
Sprint 11: Dual Output Design & Ishita Layout Integration -- 01 Jan 2027 to 14 Jan 2027
11.1 | LLM Dev | Build Output 1 -- Detailed Risk Analysis per question (qualitative, all 48 scopes) | 01-Jan-2027 | 02-Jan-2027
11.2 | LLM Dev | Build Output 2 -- Top Scope Areas Summary (qualitative + quantitative combined) | 03-Jan-2027 | 04-Jan-2027
11.3 | LLM Dev | Implement drill-down navigation structure (scope area summary to question-level detail) | 05-Jan-2027 | 06-Jan-2027
11.4 | LLM Dev | Align output column structure and layout with Ishita's confirmed specification | 07-Jan-2027 | 08-Jan-2027
11.5 | LLM Dev | Combine quantitative transactional results (NL-to-SQL) with qualitative risk output in Output 2 | 09-Jan-2027 | 10-Jan-2027
11.6 | Documentation | Update output schema documentation; share final layout with all stakeholders for sign-off | 11-Jan-2027 | 13-Jan-2027
Sprint 12: Full Simulation & Quality Assurance -- 15 Jan 2027 to 28 Jan 2027
12.1 | LLM Dev | Run full end-to-end simulation across all 48 scope areas (Planning + IDR questionnaires) | 15-Jan-2027 | 15-Jan-2027
12.2 | LLM Dev | Validate transactional data analysis -- NL-to-SQL results for all quantitative questions | 16-Jan-2027 | 17-Jan-2027
12.3 | LLM Dev | Unit testing -- all agents, retrieval tools, conflict detector and scope mapper in isolation | 18-Jan-2027 | 19-Jan-2027
12.4 | LLM Dev | Integration testing -- full pipeline end-to-end with all 5 agents and all services | 20-Jan-2027 | 21-Jan-2027
12.5 | LLM Dev | Test edge cases -- blank responses, generic responses, conflicting cross-row responses | 22-Jan-2027 | 23-Jan-2027
12.6 | LLM Dev | Bug fixes and prompt refinements based on full simulation results | 24-Jan-2027 | 25-Jan-2027
12.7 | Data Prep | Performance optimization -- async benchmarking, memory profiling, latency reduction | 26-Jan-2027 | 27-Jan-2027
Sprint 13: SME Validation & Feedback Integration -- 29 Jan 2027 to 11 Feb 2027
13.1 | Monitoring | SME review of AI-generated risk findings -- compare against actual audit outcomes | 29-Jan-2027 | 30-Jan-2027
13.2 | Monitoring | Validate risk rationale accuracy with J&J audit team across all scope areas | 31-Jan-2027 | 01-Feb-2027
13.3 | Monitoring | Cross-check evidence classification accuracy (A/B/C/D/E) with SME reviewers | 02-Feb-2027 | 03-Feb-2027
13.4 | Monitoring | Incorporate SME feedback -- prompt refinements, guardrail updates, threshold adjustments | 04-Feb-2027 | 05-Feb-2027
13.5 | Monitoring | Business UAT validation session with J&J stakeholders; document all findings | 06-Feb-2027 | 07-Feb-2027
13.6 | Monitoring | Final guardrail checks -- implement edge case handling from SME and UAT findings | 08-Feb-2027 | 10-Feb-2027
Sprint 14: Stabilization, UAT & Production Preparation -- 12 Feb 2027 to 19 Feb 2027
14.1 | Monitoring | Final prompt tuning and regression testing across all scope areas | 12-Feb-2027 | 12-Feb-2027
14.2 | Monitoring | Performance hardening -- final latency and throughput optimization | 13-Feb-2027 | 13-Feb-2027
14.3 | Deployment | Production environment setup on Databricks (Unity Catalog -- prod catalog) | 14-Feb-2027 | 14-Feb-2027
14.4 | Deployment | Security review -- Databricks secret scope, API key rotation and access controls | 15-Feb-2027 | 15-Feb-2027
14.5 | Documentation | Runbook, operational documentation and incident response guide | 16-Feb-2027 | 16-Feb-2027
14.6 | Deployment | Final UAT sign-off from J&J audit team and all named stakeholders | 17-Feb-2027 | 18-Feb-2027
Sprint 15: Production Rollout & Project Handover -- 20 Feb 2027 to 28 Feb 2027
15.1 | Deployment | Production deployment on Databricks -- execute deployment steps and validate | 20-Feb-2027 | 20-Feb-2027
15.2 | Monitoring | Monitoring setup -- pipeline failure alerts, output quality checks, Databricks job health | 21-Feb-2027 | 22-Feb-2027
15.3 | Deployment | Handover to J&J operations team -- runbook walkthrough and access transfer | 23-Feb-2027 | 23-Feb-2027
15.4 | Documentation | Final documentation update, architecture review and knowledge transfer session | 24-Feb-2027 | 25-Feb-2027
15.5 | Deployment | Post-deployment validation -- confirm pipeline runs correctly in production end-to-end | 26-Feb-2027 | 27-Feb-2027

## Sprint 1
Sprint 1: Policy & Use Case Finalization
Goal: Understand HCBI and local policies, define red flag criteria, finalize 48 scope areas and audit use cases ¦ Start: 01 May 2026 End: 28 Jun 2026
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
1.1 | Policy & Use Case | Review HCBI Global Policy (TV-POL-02257_v3.0.pdf) -- 115 pages, image-based PDF
1.1.1 | Policy & Use Case | Structured review: read and annotate all relevant policy/questionnaire sections
1.1.2 | Policy & Use Case | Extract and document key requirements, rules, scope criteria and decision logic
1.1.3 | Policy & Use Case | Peer review session with team; obtain stakeholder sign-off on documented requirements
1.2 | Policy & Use Case | Review all 7 Local Policies TPI (TPEC, Red Flag, SOP, BGS and associated documents)
1.2.1 | Policy & Use Case | Structured review: read and annotate all relevant policy/questionnaire sections
1.2.2 | Policy & Use Case | Extract and document key requirements, rules, scope criteria and decision logic
1.2.3 | Policy & Use Case | Peer review session with team; obtain stakeholder sign-off on documented requirements
1.3 | Policy & Use Case | Study Planning Questionnaire and IDR Questionnaire -- column structure and response formats
1.3.1 | Policy & Use Case | Structured review: read and annotate all relevant policy/questionnaire sections
1.3.2 | Policy & Use Case | Extract and document key requirements, rules, scope criteria and decision logic
1.3.3 | Policy & Use Case | Peer review session with team; obtain stakeholder sign-off on documented requirements
1.4 | Policy & Use Case | Define red flag criteria and risk assessment decision framework
1.4.1 | Policy & Use Case | Structured review: read and annotate all relevant policy/questionnaire sections
1.4.2 | Policy & Use Case | Extract and document key requirements, rules, scope criteria and decision logic
1.4.3 | Policy & Use Case | Peer review session with team; obtain stakeholder sign-off on documented requirements
1.5 | Policy & Use Case | Identify use cases -- risk types, compliance check scenarios, conflict detection scenarios
1.5.1 | Policy & Use Case | Structured review: read and annotate all relevant policy/questionnaire sections
1.5.2 | Policy & Use Case | Extract and document key requirements, rules, scope criteria and decision logic
1.5.3 | Policy & Use Case | Peer review session with team; obtain stakeholder sign-off on documented requirements
1.6 | Policy & Use Case | Finalize 48 scope areas; confirm TPI Due Diligence as the active MVP scope
1.6.1 | Policy & Use Case | Structured review: read and annotate all relevant policy/questionnaire sections
1.6.2 | Policy & Use Case | Extract and document key requirements, rules, scope criteria and decision logic
1.6.3 | Policy & Use Case | Peer review session with team; obtain stakeholder sign-off on documented requirements
1.7 | Documentation | Create BRD, Architecture and Flow doc, AI Auditor Documentation and Sprint Plan
1.7.1 | Documentation | Draft initial content structure, key sections and diagrams
1.7.2 | Documentation | Populate all sections; add tables, code snippets and architecture references
1.7.3 | Documentation | Peer review; finalize and distribute to all stakeholders
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 2
Sprint 2: MVP Build -- Full Pipeline for TPI Due Diligence
Goal: Build the complete end-to-end pipeline for one scope (TPI Due Diligence): all ingestion, all agents, services, transactional layer and output ¦ Start: 29 Jun 2026 End: 02 Sep 2026
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
2.1 | Data Prep | Set up config.py, settings.py and .env structure with all Azure OpenAI and Databricks variables
2.1.1 | Data Prep | Define all environment variables in .env template (Azure OpenAI, Databricks, indexes)
2.1.2 | Data Prep | Implement settings.py using pydantic-settings with full type validation
2.1.3 | Data Prep | Test config loading in local .env and Databricks secret scope environments
2.2 | Data Prep | Build schemas/state.py -- Pydantic models: QuestionRow, AuditState, RiskOutput, TransactionalQueryResult, ConflictFlag
2.2.1 | Data Prep | Define QuestionRow, RetrievedChunk, ConflictFlag and ScopeAssignment models
2.2.2 | Data Prep | Define RiskOutput, TransactionalQueryResult and AuditState TypedDict
2.2.3 | Data Prep | Validate all models with sample data; confirm JSON serialization round-trips correctly
2.3 | Data Prep | Set up azure_openai.py (GPT-5 via JNJ gateway) and embedder.py (text-embedding-3-small)
2.3.1 | Data Prep | Implement AzureChatOpenAI client wrapper (GPT-5, JNJ gateway, streaming)
2.3.2 | Data Prep | Implement AzureOpenAIEmbeddings client (text-embedding-3-small, 1536 dims)
2.3.3 | Data Prep | Test both clients with sample inputs; validate responses and token counts
2.4 | Data Prep | Build pdf_extractor.py -- pdfplumber + PyMuPDF + Azure Document Intelligence for image-based PDFs
2.4.1 | Data Prep | Implement core text extraction logic for pdf_extractor.py
2.4.2 | Data Prep | Handle edge cases: encoding errors, empty files, malformed input
2.4.3 | Data Prep | Unit test with representative sample files; validate text quality and structure
2.5 | Data Prep | Build excel_extractor.py (pandas + openpyxl) and word_extractor.py (python-docx)
2.5.1 | Data Prep | Implement core text extraction logic for excel_extractor.py (pandas + openpyxl) and word_extractor.py (python-docx)
2.5.2 | Data Prep | Handle edge cases: encoding errors, empty files, malformed input
2.5.3 | Data Prep | Unit test with representative sample files; validate text quality and structure
2.6 | Data Prep | Build ppt_extractor.py (python-pptx + OCR) and html_extractor.py (BeautifulSoup)
2.6.1 | Data Prep | Implement core text extraction logic for ppt_extractor.py (python-pptx + OCR) and html_extractor.py (BeautifulSoup)
2.6.2 | Data Prep | Handle edge cases: encoding errors, empty files, malformed input
2.6.3 | Data Prep | Unit test with representative sample files; validate text quality and structure
2.7 | Data Prep | Build email_extractor.py (extract-msg) with recursive nested attachment extraction
2.7.1 | Data Prep | Implement core text extraction logic for email_extractor.py (extract-msg) with recursive nested attachment extraction
2.7.2 | Data Prep | Handle edge cases: encoding errors, empty files, malformed input
2.7.3 | Data Prep | Unit test with representative sample files; validate text quality and structure
2.8 | Data Prep | Build document_loader.py -- universal format router with recursive directory walk for all volume paths
2.8.1 | Data Prep | Implement file format detection and extractor routing (extension + MIME type)
2.8.2 | Data Prep | Implement recursive directory walk for all nested Databricks Volume subdirectories
2.8.3 | Data Prep | Test loader on mixed-format nested directory; confirm all paths and formats covered
2.9 | Data Prep | Build chunker.py -- section-aware chunking (800 tokens max, 1-paragraph overlap)
2.9.1 | Data Prep | Implement section-boundary detection (headings, numbered clauses, paragraph breaks)
2.9.2 | Data Prep | Implement token-aware splitting: 800 token max, 1-paragraph overlap
2.9.3 | Data Prep | Validate chunk quality on HCBI (115pp) and TPI Local Policy sample documents
2.10 | Data Prep | Process HCBI Global Policy PDF (image-based, 115 pages) via Azure Document Intelligence + OCR
2.10.1 | Data Prep | Run document_loader on target volume path with recursive walk; log file counts
2.10.2 | Data Prep | Validate extracted text quality: check for OCR errors, missing sections, encoding issues
2.10.3 | Data Prep | Chunk and embed content; verify chunk count, metadata fields and embedding shape (1536)
2.11 | Data Prep | Process all 7 Local Policies TPI documents (PDFs and .doc) via document loader
2.11.1 | Data Prep | Run document_loader on target volume path with recursive walk; log file counts
2.11.2 | Data Prep | Validate extracted text quality: check for OCR errors, missing sections, encoding issues
2.11.3 | Data Prep | Chunk and embed content; verify chunk count, metadata fields and embedding shape (1536)
2.12 | Data Prep | Process Master Audit Skills PDFs (4 modules) -- load as system context into Delta table
2.12.1 | Data Prep | Run document_loader on target volume path with recursive walk; log file counts
2.12.2 | Data Prep | Validate extracted text quality: check for OCR errors, missing sections, encoding issues
2.12.3 | Data Prep | Chunk and embed content; verify chunk count, metadata fields and embedding shape (1536)
2.13 | Data Prep | Process all Supporting Documents from Databricks Volume (recursive directory walk, all formats)
2.13.1 | Data Prep | Run document_loader on target volume path with recursive walk; log file counts
2.13.2 | Data Prep | Validate extracted text quality: check for OCR errors, missing sections, encoding issues
2.13.3 | Data Prep | Chunk and embed content; verify chunk count, metadata fields and embedding shape (1536)
2.14 | Data Prep | Build vector_store.py -- Databricks Vector Search client (create, upsert, query)
2.14.1 | Data Prep | Define index schema with correct embedding dimension (1536) and metadata fields
2.14.2 | Data Prep | Batch upsert chunks into Databricks Vector Search; handle rate limits and retries
2.14.3 | Data Prep | Validate index retrieval quality: run sample queries, check top-5 precision
2.15 | Data Prep | Create and populate hcbi_index with HCBI Global Policy chunks (text-embedding-3-small, 1536 dims)
2.15.1 | Data Prep | Define index schema with correct embedding dimension (1536) and metadata fields
2.15.2 | Data Prep | Batch upsert chunks into Databricks Vector Search; handle rate limits and retries
2.15.3 | Data Prep | Validate index retrieval quality: run sample queries, check top-5 precision
2.16 | Data Prep | Create and populate due_diligence_index with TPI Local Policy chunks
2.16.1 | Data Prep | Define index schema with correct embedding dimension (1536) and metadata fields
2.16.2 | Data Prep | Batch upsert chunks into Databricks Vector Search; handle rate limits and retries
2.16.3 | Data Prep | Validate index retrieval quality: run sample queries, check top-5 precision
2.17 | Data Prep | Create and populate supporting_docs_index with Supporting Document chunks
2.17.1 | Data Prep | Define index schema with correct embedding dimension (1536) and metadata fields
2.17.2 | Data Prep | Batch upsert chunks into Databricks Vector Search; handle rate limits and retries
2.17.3 | Data Prep | Validate index retrieval quality: run sample queries, check top-5 precision
2.18 | Data Prep | Load 3 transactional data files into Delta tables: Payments, Credit Memo, Revenue (TPI scope)
2.18.1 | Data Prep | Prepare and clean raw transactional data; validate column names and data types
2.18.2 | Data Prep | Write to Delta tables using Spark; confirm schema, row counts, partitioning
2.18.3 | Data Prep | Run test NL-to-SQL query on each table; confirm TPI Due Diligence scope filter works
2.19 | LLM Dev | Build hcbi_retrieval_tool.py, policy_retrieval_tool.py, evidence_retrieval_tool.py
2.19.1 | LLM Dev | Define LangChain tool schema, decorator and input/output types
2.19.2 | LLM Dev | Implement query construction from AuditState fields (question + response text)
2.19.3 | LLM Dev | Test retrieval quality on 10 TPI Due Diligence sample questions; tune top-k
2.20 | LLM Dev | Build conflict_detector.py -- InMemoryStore cross-row semantic similarity (threshold 0.90)
2.20.1 | LLM Dev | Implement question embedding storage in LangGraph InMemoryStore (keyed by row ID)
2.20.2 | LLM Dev | Implement cosine similarity check across all stored embeddings (threshold 0.90)
2.20.3 | LLM Dev | Test conflict detection with 5 known-conflicting question pairs; validate flag output
2.21 | LLM Dev | Build policy_knowledge_agent.py -- queries hcbi_index and due_diligence_index in parallel
2.21.1 | LLM Dev | Implement asyncio.gather() parallel query to hcbi_index and due_diligence_index
2.21.2 | LLM Dev | Implement chunk merging, deduplication by chunk_id and metadata enrichment
2.21.3 | LLM Dev | Integration test: validate top-5 chunks returned are relevant for 10 HCBI/policy questions
2.22 | LLM Dev | Build evidence_assessment_agent.py -- semantic search + targeted retrieval by cited document name
2.22.1 | LLM Dev | Implement semantic search (top-5) against supporting_docs_index
2.22.2 | LLM Dev | Implement targeted metadata filter retrieval by cited document name from questionnaire row
2.22.3 | LLM Dev | Integration test dual retrieval: confirm correct evidence doc returned when doc name is cited
2.23 | LLM Dev | Build context_aggregator.py -- source hierarchy ranking (HCBI > Local Policy > Supporting Docs)
2.23.1 | LLM Dev | Implement source hierarchy ranking: HCBI (highest) > Local Policy > Supporting Docs
2.23.2 | LLM Dev | Implement relevance-score-based deduplication and chunk reranking
2.23.3 | LLM Dev | Validate aggregated_context output on 10 sample question rows
2.24 | LLM Dev | Build scope_mapper.py -- cosine similarity against 48 pre-computed scope embeddings
2.24.1 | LLM Dev | Load 48 pre-computed scope embeddings from compliance_scope_description Delta table
2.24.2 | LLM Dev | Implement cosine similarity scoring and top-1 scope assignment with confidence score
2.24.3 | LLM Dev | Validate scope assignments against manually labeled TPI Due Diligence questions
2.25 | LLM Dev | Build risk_evaluation_agent.py -- GPT-5, compliance gap identification, transactional intent detection
2.25.1 | LLM Dev | Design system prompt: embed Master Audit Skills context + HCBI compliance rules
2.25.2 | LLM Dev | Implement compliance gap identification and transactional intent detection logic
2.25.3 | LLM Dev | Integration test: validate risk_level output and transactional agent trigger on 10 questions
2.26 | LLM Dev | Build risk_analyzer_agent.py -- GPT-5, scope assignment, risk scores, final 10-point validation
2.26.1 | LLM Dev | Design final_prompt.txt with 10-point validation checklist (scope, evidence, rationale)
2.26.2 | LLM Dev | Implement scope assignment, risk score, evidence classification A-E and source detail
2.26.3 | LLM Dev | Integration test: validate final RiskOutput schema and rationale quality on 10 questions
2.27 | LLM Dev | Build transactional_data_agent.py -- NL-to-SQL, conditional trigger, TPI Due Diligence scope filter
2.27.1 | LLM Dev | Implement NL-to-SQL prompt template and GPT-5 SQL generation for all 3 table schemas
2.27.2 | LLM Dev | Implement TPI Due Diligence scope filter and Databricks SQL execution via Spark
2.27.3 | LLM Dev | Test NL-to-SQL on 10 quantitative questions; validate SQL correctness and results
2.28 | LLM Dev | Build questionnaire_repo.py, output_repo.py, scope_repo.py (Delta table read/write repositories)
2.28.1 | LLM Dev | Implement Delta table read using Spark DataFrameReader with schema validation
2.28.2 | LLM Dev | Implement Delta table write/append with ACID guarantees and error handling
2.28.3 | LLM Dev | Integration test repos against Databricks Unity Catalog development tables
2.29 | LLM Dev | Define LangGraph StateGraph in main.py -- wire all 5 agents with asyncio.gather and conditional TDA edge
2.29.1 | LLM Dev | Define all 5 agent nodes in LangGraph StateGraph (async functions)
2.29.2 | LLM Dev | Implement conditional edge for Transactional Data Agent (quantitative intent check)
2.29.3 | LLM Dev | Run StateGraph end-to-end on one sample row; verify correct node execution order
2.30 | LLM Dev | Build output_writer.py -- Part A original columns + Part B AI columns, dual output structure
2.30.1 | LLM Dev | Implement Part A: map all original questionnaire columns to output schema
2.30.2 | LLM Dev | Implement Part B: map all AI-generated fields (risk, scope, rationale, evidence)
2.30.3 | LLM Dev | Test Excel export for Output 1 (per-question) and Output 2 (scope summary); validate layout
2.31 | LLM Dev | End-to-end simulation: run full pipeline on TPI Due Diligence (Planning + IDR questionnaires)
2.31.1 | LLM Dev | Prepare full question set (Planning + IDR questionnaires) as pipeline input
2.31.2 | LLM Dev | Execute complete pipeline run; monitor all agent nodes; capture all Delta table outputs
2.31.3 | LLM Dev | Spot-check 20 output rows: risk classification, scope mapping, evidence citation quality
2.32 | LLM Dev | Validate simulation output -- risk classifications, scope assignments, evidence citations, conflict flags
2.32.1 | LLM Dev | Prepare full question set (Planning + IDR questionnaires) as pipeline input
2.32.2 | LLM Dev | Execute complete pipeline run; monitor all agent nodes; capture all Delta table outputs
2.32.3 | LLM Dev | Spot-check 20 output rows: risk classification, scope mapping, evidence citation quality
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 3
Sprint 3: Simulation Validation & MVP Hardening
Goal: Validate MVP simulation results for TPI Due Diligence, fix pipeline bugs, refine prompts and retrieval quality ¦ Start: 03 Sep 2026 End: 24 Sep 2026
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
3.1 | LLM Dev | Review all risk classifications from MVP simulation; compare against expected audit outcomes
3.1.1 | LLM Dev | Prepare full question set (Planning + IDR questionnaires) as pipeline input
3.1.2 | LLM Dev | Execute complete pipeline run; monitor all agent nodes; capture all Delta table outputs
3.1.3 | LLM Dev | Spot-check 20 output rows: risk classification, scope mapping, evidence citation quality
3.2 | LLM Dev | Assess scope mapping accuracy across all TPI Due Diligence questions
3.2.1 | LLM Dev | Design and implement: Assess scope mapping accuracy across all TPI Due Diligence questi
3.2.2 | LLM Dev | Integrate with existing pipeline; run unit tests
3.2.3 | LLM Dev | Integration test and validate output quality on sample data
3.3 | LLM Dev | Test edge cases -- blank responses, generic responses, conflicting cross-row responses
3.3.1 | LLM Dev | Design and implement: Test edge cases -- blank responses, generic responses, conflictin
3.3.2 | LLM Dev | Integrate with existing pipeline; run unit tests
3.3.3 | LLM Dev | Integration test and validate output quality on sample data
3.4 | LLM Dev | Tune retrieval parameters -- top-k, chunk size, similarity thresholds based on simulation results
3.4.1 | LLM Dev | Prepare full question set (Planning + IDR questionnaires) as pipeline input
3.4.2 | LLM Dev | Execute complete pipeline run; monitor all agent nodes; capture all Delta table outputs
3.4.3 | LLM Dev | Spot-check 20 output rows: risk classification, scope mapping, evidence citation quality
3.5 | LLM Dev | Refine prompts for Risk Evaluation Agent and Risk Analyzer Agent based on failure cases
3.5.1 | LLM Dev | Analyze prompt failure cases from simulation outputs
3.5.2 | LLM Dev | Implement targeted prompt improvements and add guardrails for identified failure modes
3.5.3 | LLM Dev | Run A/B evaluation on 20 sample questions to confirm improvement
3.6 | LLM Dev | Fix pipeline bugs and output schema issues identified in MVP simulation run
3.6.1 | LLM Dev | Prepare full question set (Planning + IDR questionnaires) as pipeline input
3.6.2 | LLM Dev | Execute complete pipeline run; monitor all agent nodes; capture all Delta table outputs
3.6.3 | LLM Dev | Spot-check 20 output rows: risk classification, scope mapping, evidence citation quality
3.7 | LLM Dev | Validate conflict detection logic -- review all flagged cross-row conflicts for accuracy
3.7.1 | LLM Dev | Define validation criteria: acceptable thresholds for risk accuracy and scope confidence
3.7.2 | LLM Dev | Execute systematic validation checks across all output rows
3.7.3 | LLM Dev | Log all issues by severity; create prioritized action items for fixes
3.8 | Data Prep | Performance testing -- async parallel retrieval benchmarking; identify and fix bottlenecks
3.8.1 | Data Prep | Profile async pipeline: measure latency per agent node on TPI Due Diligence sample
3.8.2 | Data Prep | Identify bottlenecks: retrieval, LLM calls, Delta table writes
3.8.3 | Data Prep | Implement targeted optimizations; re-benchmark and document improvements
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 4
Sprint 4: Scope Expansion -- Onboard Scope Areas 2-4
Goal: Ingest policy documents and supporting evidence for scope areas 2 to 4; run and validate simulation ¦ Start: 25 Sep 2026 End: 08 Oct 2026
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
4.1 | Policy & Use Case | Identify and collate local policy documents and supporting evidence for scope areas 2-4
4.1.1 | Policy & Use Case | Structured review: read and annotate all relevant policy/questionnaire sections
4.1.2 | Policy & Use Case | Extract and document key requirements, rules, scope criteria and decision logic
4.1.3 | Policy & Use Case | Peer review session with team; obtain stakeholder sign-off on documented requirements
4.2 | Data Prep | Ingest local policy documents for scope areas 2-4 (all formats, recursive volume walk)
4.2.1 | Data Prep | Implement: Ingest local policy documents for scope areas 2-4 (all formats, recurs
4.2.2 | Data Prep | Add error handling, logging and edge case coverage
4.2.3 | Data Prep | Test and validate output quality with representative sample data
4.3 | Data Prep | Update due_diligence_index with policy chunks for scope areas 2-4
4.3.1 | Data Prep | Define index schema with correct embedding dimension (1536) and metadata fields
4.3.2 | Data Prep | Batch upsert chunks into Databricks Vector Search; handle rate limits and retries
4.3.3 | Data Prep | Validate index retrieval quality: run sample queries, check top-5 precision
4.4 | Data Prep | Ingest and index supporting documents for scope areas 2-4 into supporting_docs_index
4.4.1 | Data Prep | Define index schema with correct embedding dimension (1536) and metadata fields
4.4.2 | Data Prep | Batch upsert chunks into Databricks Vector Search; handle rate limits and retries
4.4.3 | Data Prep | Validate index retrieval quality: run sample queries, check top-5 precision
4.5 | LLM Dev | Run simulation on questionnaire questions relevant to scope areas 2-4
4.5.1 | LLM Dev | Prepare full question set (Planning + IDR questionnaires) as pipeline input
4.5.2 | LLM Dev | Execute complete pipeline run; monitor all agent nodes; capture all Delta table outputs
4.5.3 | LLM Dev | Spot-check 20 output rows: risk classification, scope mapping, evidence citation quality
4.6 | LLM Dev | Validate output quality -- risk rationale, evidence classification, scope confidence for areas 2-4
4.6.1 | LLM Dev | Define validation criteria: acceptable thresholds for risk accuracy and scope confidence
4.6.2 | LLM Dev | Execute systematic validation checks across all output rows
4.6.3 | LLM Dev | Log all issues by severity; create prioritized action items for fixes
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 5
Sprint 5: Scope Expansion -- Onboard Scope Areas 5-8
Goal: Ingest policy documents and supporting evidence for scope areas 5 to 8; run and validate simulation ¦ Start: 09 Oct 2026 End: 22 Oct 2026
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
5.1 | Policy & Use Case | Identify and collate local policy documents and supporting evidence for scope areas 5-8
5.1.1 | Policy & Use Case | Structured review: read and annotate all relevant policy/questionnaire sections
5.1.2 | Policy & Use Case | Extract and document key requirements, rules, scope criteria and decision logic
5.1.3 | Policy & Use Case | Peer review session with team; obtain stakeholder sign-off on documented requirements
5.2 | Data Prep | Ingest local policy documents for scope areas 5-8 (all formats, recursive volume walk)
5.2.1 | Data Prep | Implement: Ingest local policy documents for scope areas 5-8 (all formats, recurs
5.2.2 | Data Prep | Add error handling, logging and edge case coverage
5.2.3 | Data Prep | Test and validate output quality with representative sample data
5.3 | Data Prep | Update due_diligence_index with policy chunks for scope areas 5-8
5.3.1 | Data Prep | Define index schema with correct embedding dimension (1536) and metadata fields
5.3.2 | Data Prep | Batch upsert chunks into Databricks Vector Search; handle rate limits and retries
5.3.3 | Data Prep | Validate index retrieval quality: run sample queries, check top-5 precision
5.4 | Data Prep | Ingest and index supporting documents for scope areas 5-8 into supporting_docs_index
5.4.1 | Data Prep | Define index schema with correct embedding dimension (1536) and metadata fields
5.4.2 | Data Prep | Batch upsert chunks into Databricks Vector Search; handle rate limits and retries
5.4.3 | Data Prep | Validate index retrieval quality: run sample queries, check top-5 precision
5.5 | LLM Dev | Run simulation on questionnaire questions relevant to scope areas 5-8
5.5.1 | LLM Dev | Prepare full question set (Planning + IDR questionnaires) as pipeline input
5.5.2 | LLM Dev | Execute complete pipeline run; monitor all agent nodes; capture all Delta table outputs
5.5.3 | LLM Dev | Spot-check 20 output rows: risk classification, scope mapping, evidence citation quality
5.6 | LLM Dev | Validate output quality -- risk rationale, evidence classification, scope confidence for areas 5-8
5.6.1 | LLM Dev | Define validation criteria: acceptable thresholds for risk accuracy and scope confidence
5.6.2 | LLM Dev | Execute systematic validation checks across all output rows
5.6.3 | LLM Dev | Log all issues by severity; create prioritized action items for fixes
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 6
Sprint 6: Scope Expansion -- Onboard Scope Areas 9-12
Goal: Ingest policy documents and supporting evidence for scope areas 9 to 12; run and validate simulation ¦ Start: 23 Oct 2026 End: 05 Nov 2026
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
6.1 | Policy & Use Case | Identify and collate local policy documents and supporting evidence for scope areas 9-12
6.1.1 | Policy & Use Case | Structured review: read and annotate all relevant policy/questionnaire sections
6.1.2 | Policy & Use Case | Extract and document key requirements, rules, scope criteria and decision logic
6.1.3 | Policy & Use Case | Peer review session with team; obtain stakeholder sign-off on documented requirements
6.2 | Data Prep | Ingest local policy documents for scope areas 9-12 (all formats, recursive volume walk)
6.2.1 | Data Prep | Implement: Ingest local policy documents for scope areas 9-12 (all formats, recur
6.2.2 | Data Prep | Add error handling, logging and edge case coverage
6.2.3 | Data Prep | Test and validate output quality with representative sample data
6.3 | Data Prep | Update due_diligence_index with policy chunks for scope areas 9-12
6.3.1 | Data Prep | Define index schema with correct embedding dimension (1536) and metadata fields
6.3.2 | Data Prep | Batch upsert chunks into Databricks Vector Search; handle rate limits and retries
6.3.3 | Data Prep | Validate index retrieval quality: run sample queries, check top-5 precision
6.4 | Data Prep | Ingest and index supporting documents for scope areas 9-12 into supporting_docs_index
6.4.1 | Data Prep | Define index schema with correct embedding dimension (1536) and metadata fields
6.4.2 | Data Prep | Batch upsert chunks into Databricks Vector Search; handle rate limits and retries
6.4.3 | Data Prep | Validate index retrieval quality: run sample queries, check top-5 precision
6.5 | LLM Dev | Run simulation on questionnaire questions relevant to scope areas 9-12
6.5.1 | LLM Dev | Prepare full question set (Planning + IDR questionnaires) as pipeline input
6.5.2 | LLM Dev | Execute complete pipeline run; monitor all agent nodes; capture all Delta table outputs
6.5.3 | LLM Dev | Spot-check 20 output rows: risk classification, scope mapping, evidence citation quality
6.6 | LLM Dev | Validate output quality and fix scope mapping issues for areas 9-12
6.6.1 | LLM Dev | Define validation criteria: acceptable thresholds for risk accuracy and scope confidence
6.6.2 | LLM Dev | Execute systematic validation checks across all output rows
6.6.3 | LLM Dev | Log all issues by severity; create prioritized action items for fixes
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 7
Sprint 7: Scope Expansion -- Onboard Scope Areas 13-18
Goal: Ingest policy documents and supporting evidence for scope areas 13 to 18; run and validate simulation ¦ Start: 06 Nov 2026 End: 19 Nov 2026
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
7.1 | Policy & Use Case | Identify and collate local policy documents and supporting evidence for scope areas 13-18
7.1.1 | Policy & Use Case | Structured review: read and annotate all relevant policy/questionnaire sections
7.1.2 | Policy & Use Case | Extract and document key requirements, rules, scope criteria and decision logic
7.1.3 | Policy & Use Case | Peer review session with team; obtain stakeholder sign-off on documented requirements
7.2 | Data Prep | Ingest local policy documents for scope areas 13-18 (all formats, recursive volume walk)
7.2.1 | Data Prep | Implement: Ingest local policy documents for scope areas 13-18 (all formats, recu
7.2.2 | Data Prep | Add error handling, logging and edge case coverage
7.2.3 | Data Prep | Test and validate output quality with representative sample data
7.3 | Data Prep | Update due_diligence_index with policy chunks for scope areas 13-18
7.3.1 | Data Prep | Define index schema with correct embedding dimension (1536) and metadata fields
7.3.2 | Data Prep | Batch upsert chunks into Databricks Vector Search; handle rate limits and retries
7.3.3 | Data Prep | Validate index retrieval quality: run sample queries, check top-5 precision
7.4 | Data Prep | Ingest and index supporting documents for scope areas 13-18 into supporting_docs_index
7.4.1 | Data Prep | Define index schema with correct embedding dimension (1536) and metadata fields
7.4.2 | Data Prep | Batch upsert chunks into Databricks Vector Search; handle rate limits and retries
7.4.3 | Data Prep | Validate index retrieval quality: run sample queries, check top-5 precision
7.5 | LLM Dev | Run simulation on questionnaire questions relevant to scope areas 13-18
7.5.1 | LLM Dev | Prepare full question set (Planning + IDR questionnaires) as pipeline input
7.5.2 | LLM Dev | Execute complete pipeline run; monitor all agent nodes; capture all Delta table outputs
7.5.3 | LLM Dev | Spot-check 20 output rows: risk classification, scope mapping, evidence citation quality
7.6 | LLM Dev | Validate output quality and fix scope mapping issues for areas 13-18
7.6.1 | LLM Dev | Define validation criteria: acceptable thresholds for risk accuracy and scope confidence
7.6.2 | LLM Dev | Execute systematic validation checks across all output rows
7.6.3 | LLM Dev | Log all issues by severity; create prioritized action items for fixes
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 8
Sprint 8: Scope Expansion -- Onboard Scope Areas 19-24
Goal: Ingest policy documents and supporting evidence for scope areas 19 to 24; run and validate simulation ¦ Start: 20 Nov 2026 End: 03 Dec 2026
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
8.1 | Policy & Use Case | Identify and collate local policy documents and supporting evidence for scope areas 19-24
8.1.1 | Policy & Use Case | Structured review: read and annotate all relevant policy/questionnaire sections
8.1.2 | Policy & Use Case | Extract and document key requirements, rules, scope criteria and decision logic
8.1.3 | Policy & Use Case | Peer review session with team; obtain stakeholder sign-off on documented requirements
8.2 | Data Prep | Ingest local policy documents for scope areas 19-24 (all formats, recursive volume walk)
8.2.1 | Data Prep | Implement: Ingest local policy documents for scope areas 19-24 (all formats, recu
8.2.2 | Data Prep | Add error handling, logging and edge case coverage
8.2.3 | Data Prep | Test and validate output quality with representative sample data
8.3 | Data Prep | Update due_diligence_index with policy chunks for scope areas 19-24
8.3.1 | Data Prep | Define index schema with correct embedding dimension (1536) and metadata fields
8.3.2 | Data Prep | Batch upsert chunks into Databricks Vector Search; handle rate limits and retries
8.3.3 | Data Prep | Validate index retrieval quality: run sample queries, check top-5 precision
8.4 | Data Prep | Ingest and index supporting documents for scope areas 19-24 into supporting_docs_index
8.4.1 | Data Prep | Define index schema with correct embedding dimension (1536) and metadata fields
8.4.2 | Data Prep | Batch upsert chunks into Databricks Vector Search; handle rate limits and retries
8.4.3 | Data Prep | Validate index retrieval quality: run sample queries, check top-5 precision
8.5 | LLM Dev | Run simulation on questionnaire questions relevant to scope areas 19-24
8.5.1 | LLM Dev | Prepare full question set (Planning + IDR questionnaires) as pipeline input
8.5.2 | LLM Dev | Execute complete pipeline run; monitor all agent nodes; capture all Delta table outputs
8.5.3 | LLM Dev | Spot-check 20 output rows: risk classification, scope mapping, evidence citation quality
8.6 | LLM Dev | Validate output quality and refine prompts for scope areas 19-24
8.6.1 | LLM Dev | Define validation criteria: acceptable thresholds for risk accuracy and scope confidence
8.6.2 | LLM Dev | Execute systematic validation checks across all output rows
8.6.3 | LLM Dev | Log all issues by severity; create prioritized action items for fixes
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 9
Sprint 9: Scope Expansion -- Onboard Scope Areas 25-36
Goal: Ingest policy documents and supporting evidence for scope areas 25 to 36; run and validate simulation ¦ Start: 04 Dec 2026 End: 17 Dec 2026
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
9.1 | Policy & Use Case | Identify and collate local policy documents and supporting evidence for scope areas 25-36
9.1.1 | Policy & Use Case | Structured review: read and annotate all relevant policy/questionnaire sections
9.1.2 | Policy & Use Case | Extract and document key requirements, rules, scope criteria and decision logic
9.1.3 | Policy & Use Case | Peer review session with team; obtain stakeholder sign-off on documented requirements
9.2 | Data Prep | Ingest local policy documents for scope areas 25-36 (all formats, recursive volume walk)
9.2.1 | Data Prep | Implement: Ingest local policy documents for scope areas 25-36 (all formats, recu
9.2.2 | Data Prep | Add error handling, logging and edge case coverage
9.2.3 | Data Prep | Test and validate output quality with representative sample data
9.3 | Data Prep | Update due_diligence_index with policy chunks for scope areas 25-36
9.3.1 | Data Prep | Define index schema with correct embedding dimension (1536) and metadata fields
9.3.2 | Data Prep | Batch upsert chunks into Databricks Vector Search; handle rate limits and retries
9.3.3 | Data Prep | Validate index retrieval quality: run sample queries, check top-5 precision
9.4 | Data Prep | Ingest and index supporting documents for scope areas 25-36 into supporting_docs_index
9.4.1 | Data Prep | Define index schema with correct embedding dimension (1536) and metadata fields
9.4.2 | Data Prep | Batch upsert chunks into Databricks Vector Search; handle rate limits and retries
9.4.3 | Data Prep | Validate index retrieval quality: run sample queries, check top-5 precision
9.5 | LLM Dev | Run simulation on questionnaire questions relevant to scope areas 25-36
9.5.1 | LLM Dev | Prepare full question set (Planning + IDR questionnaires) as pipeline input
9.5.2 | LLM Dev | Execute complete pipeline run; monitor all agent nodes; capture all Delta table outputs
9.5.3 | LLM Dev | Spot-check 20 output rows: risk classification, scope mapping, evidence citation quality
9.6 | LLM Dev | Validate output quality and fix scope mapping issues for areas 25-36
9.6.1 | LLM Dev | Define validation criteria: acceptable thresholds for risk accuracy and scope confidence
9.6.2 | LLM Dev | Execute systematic validation checks across all output rows
9.6.3 | LLM Dev | Log all issues by severity; create prioritized action items for fixes
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 10
Sprint 10: Scope Completion -- All 48 Scope Areas
Goal: Ingest documents for remaining scope areas 37-48; achieve full 48-scope coverage and run complete simulation ¦ Start: 18 Dec 2026 End: 31 Dec 2026
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
10.1 | Policy & Use Case | Identify and collate local policy documents and supporting evidence for scope areas 37-48
10.1.1 | Policy & Use Case | Structured review: read and annotate all relevant policy/questionnaire sections
10.1.2 | Policy & Use Case | Extract and document key requirements, rules, scope criteria and decision logic
10.1.3 | Policy & Use Case | Peer review session with team; obtain stakeholder sign-off on documented requirements
10.2 | Data Prep | Ingest local policy documents for scope areas 37-48 (all formats, recursive volume walk)
10.2.1 | Data Prep | Implement: Ingest local policy documents for scope areas 37-48 (all formats, recu
10.2.2 | Data Prep | Add error handling, logging and edge case coverage
10.2.3 | Data Prep | Test and validate output quality with representative sample data
10.3 | Data Prep | Update due_diligence_index and supporting_docs_index for scope areas 37-48
10.3.1 | Data Prep | Define index schema with correct embedding dimension (1536) and metadata fields
10.3.2 | Data Prep | Batch upsert chunks into Databricks Vector Search; handle rate limits and retries
10.3.3 | Data Prep | Validate index retrieval quality: run sample queries, check top-5 precision
10.4 | LLM Dev | Run full simulation across all 48 scope areas (Planning + IDR questionnaires)
10.4.1 | LLM Dev | Prepare full question set (Planning + IDR questionnaires) as pipeline input
10.4.2 | LLM Dev | Execute complete pipeline run; monitor all agent nodes; capture all Delta table outputs
10.4.3 | LLM Dev | Spot-check 20 output rows: risk classification, scope mapping, evidence citation quality
10.5 | LLM Dev | Validate coverage -- confirm all questions are correctly scope-mapped across all 48 areas
10.5.1 | LLM Dev | Define validation criteria: acceptable thresholds for risk accuracy and scope confidence
10.5.2 | LLM Dev | Execute systematic validation checks across all output rows
10.5.3 | LLM Dev | Log all issues by severity; create prioritized action items for fixes
10.6 | LLM Dev | Cross-scope consistency check -- verify consistent risk classification logic across all 48 scopes
10.6.1 | LLM Dev | Design and implement: Cross-scope consistency check -- verify consistent risk classific
10.6.2 | LLM Dev | Integrate with existing pipeline; run unit tests
10.6.3 | LLM Dev | Integration test and validate output quality on sample data
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 11
Sprint 11: Dual Output Design & Ishita Layout Integration
Goal: Build and finalize Output 1 (detailed per question) and Output 2 (top scope areas summary); align with Ishita output layout ¦ Start: 01 Jan 2027 End: 14 Jan 2027
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
11.1 | LLM Dev | Build Output 1 -- Detailed Risk Analysis per question (qualitative, all 48 scopes)
11.1.1 | LLM Dev | Design output structure and column mapping for specified output type
11.1.2 | LLM Dev | Implement output generation logic in output_writer.py
11.1.3 | LLM Dev | Validate output against sample data; confirm all fields populate correctly
11.2 | LLM Dev | Build Output 2 -- Top Scope Areas Summary (qualitative + quantitative combined)
11.2.1 | LLM Dev | Design output structure and column mapping for specified output type
11.2.2 | LLM Dev | Implement output generation logic in output_writer.py
11.2.3 | LLM Dev | Validate output against sample data; confirm all fields populate correctly
11.3 | LLM Dev | Implement drill-down navigation structure (scope area summary to question-level detail)
11.3.1 | LLM Dev | Design navigation structure: scope summary sheet linked to question-level detail
11.3.2 | LLM Dev | Implement Excel hyperlinks or index sheet for drill-down navigation
11.3.3 | LLM Dev | Test navigation with stakeholder; confirm auditor can drill down from scope to question
11.4 | LLM Dev | Align output column structure and layout with Ishita's confirmed specification
11.4.1 | LLM Dev | Design and implement: Align output column structure and layout with Ishita's confirmed
11.4.2 | LLM Dev | Integrate with existing pipeline; run unit tests
11.4.3 | LLM Dev | Integration test and validate output quality on sample data
11.5 | LLM Dev | Combine quantitative transactional results (NL-to-SQL) with qualitative risk output in Output 2
11.5.1 | LLM Dev | Design output structure and column mapping for specified output type
11.5.2 | LLM Dev | Implement output generation logic in output_writer.py
11.5.3 | LLM Dev | Validate output against sample data; confirm all fields populate correctly
11.6 | Documentation | Update output schema documentation; share final layout with all stakeholders for sign-off
11.6.1 | Documentation | Draft initial content structure, key sections and diagrams
11.6.2 | Documentation | Populate all sections; add tables, code snippets and architecture references
11.6.3 | Documentation | Peer review; finalize and distribute to all stakeholders
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 12
Sprint 12: Full Simulation & Quality Assurance
Goal: Run complete simulation across all 48 scope areas with transactional analysis; comprehensive end-to-end QA ¦ Start: 15 Jan 2027 End: 28 Jan 2027
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
12.1 | LLM Dev | Run full end-to-end simulation across all 48 scope areas (Planning + IDR questionnaires)
12.1.1 | LLM Dev | Prepare full question set (Planning + IDR questionnaires) as pipeline input
12.1.2 | LLM Dev | Execute complete pipeline run; monitor all agent nodes; capture all Delta table outputs
12.1.3 | LLM Dev | Spot-check 20 output rows: risk classification, scope mapping, evidence citation quality
12.2 | LLM Dev | Validate transactional data analysis -- NL-to-SQL results for all quantitative questions
12.2.1 | LLM Dev | Define validation criteria: acceptable thresholds for risk accuracy and scope confidence
12.2.2 | LLM Dev | Execute systematic validation checks across all output rows
12.2.3 | LLM Dev | Log all issues by severity; create prioritized action items for fixes
12.3 | LLM Dev | Unit testing -- all agents, retrieval tools, conflict detector and scope mapper in isolation
12.3.1 | LLM Dev | Define LangChain tool schema, decorator and input/output types
12.3.2 | LLM Dev | Implement query construction from AuditState fields (question + response text)
12.3.3 | LLM Dev | Test retrieval quality on 10 TPI Due Diligence sample questions; tune top-k
12.4 | LLM Dev | Integration testing -- full pipeline end-to-end with all 5 agents and all services
12.4.1 | LLM Dev | Prepare full question set (Planning + IDR questionnaires) as pipeline input
12.4.2 | LLM Dev | Execute complete pipeline run; monitor all agent nodes; capture all Delta table outputs
12.4.3 | LLM Dev | Spot-check 20 output rows: risk classification, scope mapping, evidence citation quality
12.5 | LLM Dev | Test edge cases -- blank responses, generic responses, conflicting cross-row responses
12.5.1 | LLM Dev | Design and implement: Test edge cases -- blank responses, generic responses, conflictin
12.5.2 | LLM Dev | Integrate with existing pipeline; run unit tests
12.5.3 | LLM Dev | Integration test and validate output quality on sample data
12.6 | LLM Dev | Bug fixes and prompt refinements based on full simulation results
12.6.1 | LLM Dev | Prepare full question set (Planning + IDR questionnaires) as pipeline input
12.6.2 | LLM Dev | Execute complete pipeline run; monitor all agent nodes; capture all Delta table outputs
12.6.3 | LLM Dev | Spot-check 20 output rows: risk classification, scope mapping, evidence citation quality
12.7 | Data Prep | Performance optimization -- async benchmarking, memory profiling, latency reduction
12.7.1 | Data Prep | Profile async pipeline: measure latency per agent node on TPI Due Diligence sample
12.7.2 | Data Prep | Identify bottlenecks: retrieval, LLM calls, Delta table writes
12.7.3 | Data Prep | Implement targeted optimizations; re-benchmark and document improvements
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 13
Sprint 13: SME Validation & Feedback Integration
Goal: SME review of AI findings, incorporate feedback into prompts and guardrails, business UAT and sign-off ¦ Start: 29 Jan 2027 End: 11 Feb 2027
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
13.1 | Monitoring | SME review of AI-generated risk findings -- compare against actual audit outcomes
13.1.1 | Monitoring | Prepare review pack: AI output samples vs expected outcomes for reviewers
13.1.2 | Monitoring | Conduct SME review session; document all discrepancies and incorrect classifications
13.1.3 | Monitoring | Prioritize feedback; create action log and feed into prompt/threshold refinements
13.2 | Monitoring | Validate risk rationale accuracy with J&J audit team across all scope areas
13.2.1 | Monitoring | Define evaluation criteria and success metrics
13.2.2 | Monitoring | Execute monitoring/review activities; capture all findings
13.2.3 | Monitoring | Document results; create prioritized action items for improvement
13.3 | Monitoring | Cross-check evidence classification accuracy (A/B/C/D/E) with SME reviewers
13.3.1 | Monitoring | Prepare review pack: AI output samples vs expected outcomes for reviewers
13.3.2 | Monitoring | Conduct SME review session; document all discrepancies and incorrect classifications
13.3.3 | Monitoring | Prioritize feedback; create action log and feed into prompt/threshold refinements
13.4 | Monitoring | Incorporate SME feedback -- prompt refinements, guardrail updates, threshold adjustments
13.4.1 | Monitoring | Prepare review pack: AI output samples vs expected outcomes for reviewers
13.4.2 | Monitoring | Conduct SME review session; document all discrepancies and incorrect classifications
13.4.3 | Monitoring | Prioritize feedback; create action log and feed into prompt/threshold refinements
13.5 | Monitoring | Business UAT validation session with J&J stakeholders; document all findings
13.5.1 | Monitoring | Prepare UAT test scenarios, expected results and acceptance criteria
13.5.2 | Monitoring | Conduct UAT session with J&J audit team; record all findings
13.5.3 | Monitoring | Resolve UAT findings; obtain formal written sign-off from business stakeholders
13.6 | Monitoring | Final guardrail checks -- implement edge case handling from SME and UAT findings
13.6.1 | Monitoring | Prepare review pack: AI output samples vs expected outcomes for reviewers
13.6.2 | Monitoring | Conduct SME review session; document all discrepancies and incorrect classifications
13.6.3 | Monitoring | Prioritize feedback; create action log and feed into prompt/threshold refinements
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 14
Sprint 14: Stabilization, UAT & Production Preparation
Goal: Final prompt tuning, performance hardening, security review and production environment setup on Databricks ¦ Start: 12 Feb 2027 End: 19 Feb 2027
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
14.1 | Monitoring | Final prompt tuning and regression testing across all scope areas
14.1.1 | Monitoring | Define evaluation criteria and success metrics
14.1.2 | Monitoring | Execute monitoring/review activities; capture all findings
14.1.3 | Monitoring | Document results; create prioritized action items for improvement
14.2 | Monitoring | Performance hardening -- final latency and throughput optimization
14.2.1 | Monitoring | Profile pipeline: measure latency, throughput and memory across all pipeline stages
14.2.2 | Monitoring | Implement targeted optimizations based on profiling results
14.2.3 | Monitoring | Re-run benchmark; confirm improvements meet performance targets
14.3 | Deployment | Production environment setup on Databricks (Unity Catalog -- prod catalog)
14.3.1 | Deployment | Pre-deployment checklist: env variables, secrets, cluster config, access permissions
14.3.2 | Deployment | Execute production deployment on Databricks; run smoke test pipeline
14.3.3 | Deployment | Post-deployment validation: run sample questionnaire; confirm output lands in Delta table
14.4 | Deployment | Security review -- Databricks secret scope, API key rotation and access controls
14.4.1 | Deployment | Audit Databricks secret scope: confirm all API keys stored securely, not in code
14.4.2 | Deployment | Review Unity Catalog access controls; confirm least-privilege for all service principals
14.4.3 | Deployment | Document security posture; obtain security review sign-off from J&J IT
14.5 | Documentation | Runbook, operational documentation and incident response guide
14.5.1 | Documentation | Draft initial content structure, key sections and diagrams
14.5.2 | Documentation | Populate all sections; add tables, code snippets and architecture references
14.5.3 | Documentation | Peer review; finalize and distribute to all stakeholders
14.6 | Deployment | Final UAT sign-off from J&J audit team and all named stakeholders
14.6.1 | Deployment | Pre-deployment setup and environment configuration
14.6.2 | Deployment | Execute deployment steps and run validation checks
14.6.3 | Deployment | Document completion and confirm readiness with stakeholders
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 15
Sprint 15: Production Rollout & Project Handover
Goal: Deploy to production, set up monitoring and alerting, complete knowledge transfer and project closure ¦ Start: 20 Feb 2027 End: 28 Feb 2027
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
15.1 | Deployment | Production deployment on Databricks -- execute deployment steps and validate
15.1.1 | Deployment | Pre-deployment checklist: env variables, secrets, cluster config, access permissions
15.1.2 | Deployment | Execute production deployment on Databricks; run smoke test pipeline
15.1.3 | Deployment | Post-deployment validation: run sample questionnaire; confirm output lands in Delta table
15.2 | Monitoring | Monitoring setup -- pipeline failure alerts, output quality checks, Databricks job health
15.2.1 | Monitoring | Define evaluation criteria and success metrics
15.2.2 | Monitoring | Execute monitoring/review activities; capture all findings
15.2.3 | Monitoring | Document results; create prioritized action items for improvement
15.3 | Deployment | Handover to J&J operations team -- runbook walkthrough and access transfer
15.3.1 | Deployment | Prepare handover pack: runbook, architecture diagram, access list, known issues
15.3.2 | Deployment | Conduct handover walkthrough session with J&J operations team
15.3.3 | Deployment | Confirm ops team can independently trigger, monitor and troubleshoot pipeline
15.4 | Documentation | Final documentation update, architecture review and knowledge transfer session
15.4.1 | Documentation | Draft initial content structure, key sections and diagrams
15.4.2 | Documentation | Populate all sections; add tables, code snippets and architecture references
15.4.3 | Documentation | Peer review; finalize and distribute to all stakeholders
15.5 | Deployment | Post-deployment validation -- confirm pipeline runs correctly in production end-to-end
15.5.1 | Deployment | Pre-deployment checklist: env variables, secrets, cluster config, access permissions
15.5.2 | Deployment | Execute production deployment on Databricks; run smoke test pipeline
15.5.3 | Deployment | Post-deployment validation: run sample questionnaire; confirm output lands in Delta table
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation