## Management View
Enterprise AI Audit Recommendation Engine -- Sprint Plan
Project: JNJ TPI Due Diligence ¦ Platform: Databricks (Unity Catalog) ¦ Sprint Window: 27 Aug 2026 -- 05 Oct 2026 ¦ Demo: 09 Sep 2026 ¦ Version: v4
Sprint # | Sprint Name | Goal | Start Date | End Date | Duration | Tasks | Phase
Sprint 1 | Pipeline Core & Ingestion | Complete 8-agent LangGraph pipeline; all 4 vector indexes (hcbi, policy, supporting, scope_policy); multi-auditor docs; AUDITOR_ID env routing; guardrails; Dockerfile + README | 27-Aug-2026 | 02-Sep-2026 | 1 week | 8 | MVP Completion
Sprint 2 | Retrieval Intelligence & Demo Preparation | BM25Reranker + MQR hybrid retrieval; async aretrieve() on all 4 tools; ScopeIdentifier confidence threshold; end-to-end simulation for 9 scope areas; retrieval evaluation; internal demo on Sep 9 | 03-Sep-2026 | 09-Sep-2026 | 1 week | 8 | Retrieval & Demo
Sprint 3 | AI Scope & Scoping Deck Automation | AI Scope module (Output C -> per-scope Overall Risk Category from avg Likelihood x Impact, proposed sample size from CPR guidance, AI risk summary); Scoping Deck foundation -- questionnaire + supporting-docs ingestion (questionnaire_index); config-driven python-pptx renderer with J&J brand fonts / footer / locked logo; Slide 1 (Opening) and Slide 2 (Market Overview + live CPI) | 10-Sep-2026 | 16-Sep-2026 | 1 week | 8 | Scoping Deck & AI Scope
Sprint 4 | Scoping Deck Content Slides & Hardening | Business Overview (6-section table); Prior CPR & Prior GACS from Output E (past_review_gacs_and_cpr_index, CPR/GACS classification, thematic condensing, dynamic tables); remaining slides toward the 10-slide deck; performance (concurrency, retrieve-once) and robustness (fail-soft, corporate-SSL CPI); API status label mapping | 17-Sep-2026 | 23-Sep-2026 | 1 week | 8 | Scoping Deck & AI Scope
Sprint 5 | FastAPI Layer & API Hardening | Build production-ready FastAPI serving layer: /audit, /status, /health endpoints; AuditRequest/AuditResponse schemas; X-API-Key auth middleware; input sanitization; rate limiting; OpenAPI spec; post-demo prompt refinement | 24-Sep-2026 | 30-Sep-2026 | 1 week | 8 | FastAPI & API
Sprint 6 | Deployment, Scope Expansion & Benchmarking | Databricks production job configuration; Docker containerization; CI/CD via GitHub Actions; structured logging and alerting; ingest scope areas 2-9; offline retrieval evaluation (precision@k, recall@k); async performance benchmarking | 01-Oct-2026 | 05-Oct-2026 | 1 week | 8 | Deployment & Expansion
*** DEMO MILESTONE: 09 Sep 2026 -- Internal Demo, 9 Scope Areas (end of Sprint 2) ***

## Gantt Chart
Gantt Chart -- Enterprise AI Audit Recommendation Engine (27 Aug 2026 -- 05 Oct 2026)
Task Ref | Category | Task Description | Start Date | End Date
Sprint 1: Pipeline Core & Ingestion -- 27-Aug-2026 to 02-Sep-2026
1.1 | Data Prep | Settings, index names & AUDITOR_ID env routing -- remove hardcoded auditor; fresh v2 index names | 27-Aug-2026 | 02-Sep-2026
1.1.1 | Data Prep | Remove current_auditor_folder from settings.py; read AUDITOR_ID from env at startup; raise clear error if missing
1.1.2 | Data Prep | Update all 4 index names to v2: hcbi_policy_index, tpi_due_diligence_index, auditor_supporting_docs_index, fcpa_scope_policy_index
1.1.3 | Data Prep | Validate settings load from .env locally and from Databricks secret scope; confirm AUDITOR_ID flows to EvidenceRetrievalTool
1.2 | Data Prep | Vector index manager -- auditor_folder column; is_populated_any(); schema v2 for all 4 indexes | 27-Aug-2026 | 02-Sep-2026
1.2.1 | Data Prep | Add auditor_folder: string column to all 4 index schemas in ensure_index(); update upsert_chunks() to write auditor_folder field
1.2.2 | Data Prep | Implement is_populated_any(index_key): epsilon-vector probe without scope_id filter for supporting and scope_policy indexes
1.2.3 | Data Prep | Update result parsing: auditor_folder at column 13; similarity_score at column 14; handle len(row) guards
1.3 | Data Prep | Multi-auditor supporting docs ingestion -- per-subfolder tagging with auditor_folder; all auditors in one index | 27-Aug-2026 | 02-Sep-2026
1.3.1 | Data Prep | _ensure_supporting_docs_index(): iterate auditor subfolders (Sam_1, Kaitlyn_1, Naeem_1 ...) under auditors_supporting_documents volume
1.3.2 | Data Prep | Tag every chunk via model_copy(update={'auditor_folder': folder_name}); log per-folder doc and chunk counts
1.3.3 | Data Prep | Validate index populated for all auditor folders; run filtered query per auditor; confirm isolation between folders
1.4 | Data Prep | fcpa_scope_policy_index -- CPRScopeExtractor producing 96 chunks (risk_profile + audit_guidance per scope area) | 27-Aug-2026 | 02-Sep-2026
1.4.1 | Data Prep | Build CPRScopeExtractor: 48-sheet-to-scope-ID mapping; extract cols C+D+E+P (risk_profile) and F+O (audit_guidance) per sheet; skip 3 header rows
1.4.2 | Data Prep | _ensure_scope_policy_index(): download CPR Excel from volume, extract chunks, batch upsert to fcpa_scope_policy_index
1.4.3 | Data Prep | Validate 96 chunks indexed (48 scope areas x 2 chunk types); run sample scope-filtered queries; confirm top-2 retrieval precision
1.5 | LLM Dev | 8-agent LangGraph pipeline -- Phase 0 scope routing → Phase A parallel retrieval → Phase B sequential analysis | 27-Aug-2026 | 02-Sep-2026
1.5.1 | LLM Dev | Phase 0: ScopeIdentifierAgent with 48 FCPA scope areas, 4-line output format (Primary, Additional, Reasoning, Confidence)
1.5.2 | LLM Dev | Phase A: asyncio.gather(HcbiPolicyAgent, PolicyKnowledgeAgent, SupportingDocsAgent) -- fully parallel, non-blocking
1.5.3 | LLM Dev | Phase B: RiskEvaluationAgent → TransactionalDataAgent (conditional) → RiskClassifierAgent → RiskWriterAgent -- sequential
1.6 | LLM Dev | PolicyKnowledgeAgent dual-tool routing -- retrieve_scope_area_policy always; retrieve_due_diligence_policy for DUE_DILIGENCE scope only | 27-Aug-2026 | 02-Sep-2026
1.6.1 | LLM Dev | Tool 1: retrieve_scope_area_policy(query, scope_id) → ScopePolicyRetrievalTool (fcpa_scope_policy_index, top_k=2)
1.6.2 | LLM Dev | Tool 2: retrieve_due_diligence_policy(query) → PolicyRetrievalTool (tpi_due_diligence_index), called ONLY when scope = DUE_DILIGENCE
1.6.3 | LLM Dev | Update policy_knowledge_prompt: document both tools, routing rule, dual output format (SCOPE AREA POLICY + DUE DILIGENCE POLICY sections)
1.7 | LLM Dev | Universal guardrails on all 8 agent prompts -- G1-G10 covering hallucination, bias, format, scope and confidence | 27-Aug-2026 | 02-Sep-2026
1.7.1 | LLM Dev | Implement guardrails.py: UNIVERSAL block G1-G6 (no hallucination, no invented data, FCPA only, no advice, no PII, no bias)
1.7.2 | LLM Dev | Add scope-specific guardrails: G7 (valid scope IDs only), G8 (exact 4-line format), G9 (no risk assessment in scope agent), G10 (confidence calibration)
1.7.3 | LLM Dev | Apply guardrail block to all 8 agent system prompts; run py_compile on all prompt files; verify guardrail text in each compiled prompt
1.8 | Deployment | Dockerfile + README + runner entry points -- main.py ingestion + all phases; resume_from_idr.py IDR resume | 27-Aug-2026 | 02-Sep-2026
1.8.1 | Deployment | Multi-stage Dockerfile: Python 3.11 slim base, requirements.txt install, src/ copy, AUDITOR_ID + Azure/Databricks env vars, non-root user
1.8.2 | Deployment | README: architecture diagram, setup steps, .env template, how to run ingestion vs full audit, AUDITOR_ID usage, Databricks job setup
1.8.3 | Deployment | Validate both main.py and resume_from_idr.py read AUDITOR_ID from env; raise RuntimeError with clear message if missing; output filename includes auditor ID
Sprint 2: Retrieval Intelligence & Demo Prep -- 03-Sep-2026 to 09-Sep-2026
2.1 | LLM Dev | BM25Reranker -- BM25Okapi RRF fusion on EvidenceRetrievalTool; top_k*4 candidate pool | 03-Sep-2026 | 09-Sep-2026
2.1.1 | LLM Dev | Build BM25Reranker using rank-bm25: BM25Okapi corpus, RRF score = 1/(60+sem_rank) + 1/(60+bm25_rank); return top_k by RRF
2.1.2 | LLM Dev | Wire into EvidenceRetrievalTool.retrieve(): fetch candidate_k = top_k*4 from semantic search; BM25 rerank candidate pool to top_k
2.1.3 | LLM Dev | Validate on 15 evidence queries with specific document names (e.g. Starters_Leavers_Report_Q3.pdf); confirm BM25 corrects semantic ranking misses
2.2 | LLM Dev | MultiQueryRetriever extension -- MQR on HCBI (n=2), Policy (n=2), Evidence (n=3); deduplication by similarity_score | 03-Sep-2026 | 09-Sep-2026
2.2.1 | LLM Dev | Extend MQR to HcbiRetrievalTool (n=2) and PolicyRetrievalTool (n=2); EvidenceRetrievalTool already uses n=3
2.2.2 | LLM Dev | MQR deduplication: keep highest similarity_score per chunk_id across all query variants before returning top_k
2.2.3 | LLM Dev | Validate MQR improves recall@5 on 20 test queries across HCBI and Policy indexes; confirm no duplicate chunks in result
2.3 | LLM Dev | Async retrieval pipeline -- aretrieve() on all 4 tools; MQR async with asyncio.gather; Phase A fully non-blocking | 03-Sep-2026 | 09-Sep-2026
2.3.1 | LLM Dev | MQR.aretrieve(): generate alternatives via LLM.ainvoke(); run all searches in parallel via asyncio.gather + asyncio.to_thread
2.3.2 | LLM Dev | Add aretrieve() to HcbiRetrievalTool, PolicyRetrievalTool, ScopePolicyRetrievalTool; EvidenceRetrievalTool adds aretrieve_targeted()
2.3.3 | LLM Dev | Benchmark Phase A: compare wall-clock latency sync vs async for parallel hcbi+policy+supporting retrieval on 10 sample questions
2.4 | LLM Dev | ScopeIdentifier confidence threshold & retry -- confidence < 0.70 fallback to DUE_DILIGENCE; retry once on empty result | 03-Sep-2026 | 09-Sep-2026
2.4.1 | LLM Dev | Update scope_identifier_prompt: add G10 confidence calibration rule (high >= 0.85 / moderate 0.70-0.84 / low < 0.70); add Confidence line to OUTPUT FORMAT
2.4.2 | LLM Dev | Update supervisor._run_scope_identification(): parse confidence from 4th output line; retry once if no scopes returned; fall back to DUE_DILIGENCE if confidence < 0.70
2.4.3 | LLM Dev | Validate on 10 ambiguous questions: confirm DUE_DILIGENCE fallback triggers correctly; log confidence scores and retry events
2.5 | LLM Dev | Demo data preparation -- Planning + IDR questionnaire for 9 demo scope areas; all indexes verified populated | 03-Sep-2026 | 09-Sep-2026
2.5.1 | LLM Dev | Set AUDITOR_ID env var for demo auditor; confirm all 4 indexes populated (run is_populated checks); load questionnaire rows for 9 scope areas
2.5.2 | LLM Dev | Run python main.py end-to-end; monitor Phase 0 scope routing for all 9 scopes; capture output Excel
2.5.3 | LLM Dev | Review all output rows: verify scope routing accuracy, risk classifications, HCBI citations and evidence document references
2.6 | LLM Dev | Simulation review and prompt tuning -- fix scope misroutes and risk writer gaps identified in demo run | 03-Sep-2026 | 09-Sep-2026
2.6.1 | LLM Dev | Analyze simulation output: catalog scope misroutes, low-confidence assignments, hallucinated citations, weak rationale
2.6.2 | LLM Dev | Apply targeted prompt fixes to scope_identifier_prompt and risk_writer_prompt; add guardrails for newly observed failure modes
2.6.3 | LLM Dev | Re-run simulation on corrected pipeline; confirm improvement on previously failing questions; no regressions on passing ones
2.7 | ML Dev | Retrieval evaluation -- precision@k and recall@k across all 4 indexes using retrieval_evaluator.py | 03-Sep-2026 | 09-Sep-2026
2.7.1 | ML Dev | Build evaluation dataset: 10 queries per scope area with known-relevant chunk IDs for all 9 demo scopes
2.7.2 | ML Dev | Run precision@5 and recall@5 per index; tune top_k_hcbi, top_k_policy, top_k_supporting if below 0.70 precision
2.7.3 | ML Dev | Document final retrieval parameters and evaluation scores; include in demo reference pack
2.8 | Documentation | Demo script, rehearsal and stakeholder narrative -- dry-run all 9 scopes; one-pager for stakeholders | 03-Sep-2026 | 09-Sep-2026
2.8.1 | Documentation | Write demo script: auditor ID, 9 scope areas, key questions to highlight, expected risk findings and evidence citations
2.8.2 | Documentation | Full pipeline dry-run: time end-to-end for all 9 scopes; target < 4 min per question; fix any last-minute issues
2.8.3 | Documentation | Prepare stakeholder one-pager: 8-agent architecture overview, what the AI does, how scope routing works, sample output row
Sprint 3: AI Scope & Scoping Deck Automation -- 10-Sep-2026 to 16-Sep-2026
3.1 | Data Prep | AI Scope Output C loader -- Excel 3rd sheet / Delta table source config | 10-Sep-2026 | 16-Sep-2026
3.1.1 | Data Prep | Source config (EXCEL ¦ DB_TABLE) via env; resolve Output C from workbook 3rd sheet or Delta table
3.1.2 | Data Prep | Normalize headers to internal keys (Scope Area, Risk Type, Likelihood, Impact, Risk Description)
3.1.3 | Data Prep | Load rows into typed objects; validate required columns present; log row count
3.2 | ML Dev | Overall Risk Category & proposed sample size (deterministic) | 10-Sep-2026 | 16-Sep-2026
3.2.1 | ML Dev | Group Output C by scope area; score = Likelihood x Impact per risk; average across the scope
3.2.2 | ML Dev | Map averaged score to band (>=15 High, >=10 Medium, else Low); blank when no L/I present
3.2.3 | ML Dev | Fetch proposed sample size from CPR guidance workbook (col K) per scope; no buffer; volume download
3.3 | LLM Dev | AI Scope risk summary + Excel output | 10-Sep-2026 | 16-Sep-2026
3.3.1 | LLM Dev | Per-scope LLM summary (bullets) of risk descriptions; note past-audit/SI/Legal similarity if present
3.3.2 | LLM Dev | Write AI Scope Excel: Scope Area, Overall Risk Category, Proposed Sample Size, Summary of Risks
3.3.3 | LLM Dev | Validate against a sample audit; run end-to-end for Sam_1
3.4 | Data Prep | Scoping Deck questionnaire ingestion (slide_1) | 10-Sep-2026 | 16-Sep-2026
3.4.1 | Data Prep | QuestionnaireIndexManager: create questionnaire_index; push IDR + Planning Q&A with metadata
3.4.2 | Data Prep | Ensure auditor supporting docs in shared auditor_supporting_docs_index (reuse pipeline helper)
3.4.3 | Data Prep | Idempotent checks (skip if populated per auditor); retrieval sanity check
3.5 | Deployment | Config-driven python-pptx deck renderer | 10-Sep-2026 | 16-Sep-2026
3.5.1 | Deployment | DeckSpec (SlideSpec / FieldSpec / FieldKind) + DeckRenderer; 16:9 blank layout
3.5.2 | Deployment | J&J brand fonts (Johnson Display Headings / Johnson Text Body) applied per field spec
3.5.3 | Deployment | Bulleted body with **bold** markup, justified spacing; multi-line text fields
3.6 | Deployment | Common footer + locked logo | 10-Sep-2026 | 16-Sep-2026
3.6.1 | Deployment | Footer on every slide: J&J logo, Attorney-Client Privilege, Global Audit & Assurance, page number
3.6.2 | Deployment | Insert JNJ shorthand logo (fixed 0.45 x 0.19in) and lock (noMove / noResize / noSelect)
3.6.3 | Deployment | Fonts/colours per spec (#EB1700 header, #564C47 footer); verify render
3.7 | LLM Dev | Slide 1 Opening + Slide 2 Market Overview generator | 10-Sep-2026 | 16-Sep-2026
3.7.1 | LLM Dev | Opening slide: <Entity> <MRC> Compliance Process Review (2-line), review period, current date
3.7.2 | LLM Dev | Market context retriever (questionnaire + supporting docs) + reference library (prior overviews)
3.7.3 | LLM Dev | Market Overview generator (SAM only, 8-10 bullets, grounded, reference-styled)
3.8 | LLM Dev | CPI live integration (Slide 2) | 10-Sep-2026 | 16-Sep-2026
3.8.1 | LLM Dev | Resolve TI data file URL from CPI page HTML; download xlsx in-memory (ephemeral); namespace-fix parse
3.8.2 | LLM Dev | Read country by ISO3 from timeseries; two most recent years; more/less-corrupt rule; dynamic year
3.8.3 | LLM Dev | Corporate SSL handling (OS trust store / CA bundle / override); merge CPI under Market Overview (8pt gap)
Sprint 4: Scoping Deck Content Slides & Hardening -- 17-Sep-2026 to 23-Sep-2026
4.1 | LLM Dev | Slide 3 Business Overview -- 6-section generator | 17-Sep-2026 | 23-Sep-2026
4.1.1 | LLM Dev | One structured LLM call -> 6 sections (Overview, Changes, Go-to-Market, Interactions, TPI, Regulations)
4.1.2 | LLM Dev | Ground in IDR + questionnaire + supporting docs; reference-styled from prior Business Overview slides
4.1.3 | LLM Dev | Cap section length (2-4 bullets) to fit; bold key terms
4.2 | Deployment | Business Overview table rendering | 17-Sep-2026 | 23-Sep-2026
4.2.1 | Deployment | TableField + renderer: merged red header (Business Summary - <Entity>), six topic rows
4.2.2 | Deployment | Topic cell (bold 12) + content cell (11) with bullets; cell borders/fills
4.2.3 | Deployment | Fit within one slide; fonts per spec
4.3 | Data Prep | Output E ingestion -> past_review_gacs_and_cpr_index | 17-Sep-2026 | 23-Sep-2026
4.3.1 | Data Prep | Output E loader (Excel/DB); classify each observation CPR vs GACS by report terms (CPR/MAP; GACS)
4.3.2 | Data Prep | PastReviewIndexManager: create index; upsert metadata (scope, description, criticality, year, kind)
4.3.3 | Data Prep | Idempotent ingest (skip if populated per auditor)
4.4 | LLM Dev | Prior CPR & GACS builder | 17-Sep-2026 | 23-Sep-2026
4.4.1 | LLM Dev | Fetch all observations by kind; top-level scope grouping (e.g. 'FFS - X' -> 'FFS')
4.4.2 | LLM Dev | Thematic condense to adaptive 2-3 bullets per scope (one LLM call per slide); keep criticality
4.4.3 | LLM Dev | Report year from chunks; fail-soft fallback to first findings
4.5 | Deployment | Prior CPR / GACS slides (7-8) -- dynamic tables | 17-Sep-2026 | 23-Sep-2026
4.5.1 | Deployment | DynamicTableField + renderer; header 'Findings from previous CPR / GACS <Year>'
4.5.2 | Deployment | Skip-empty slide when no findings; sequential page numbering
4.5.3 | Deployment | Validate one-page fit for both
4.6 | LLM Dev | Remaining slides toward the 10-slide deck | 17-Sep-2026 | 23-Sep-2026
4.6.1 | LLM Dev | Areas in Scope - Proposed (table sourced from AI Scope output)
4.6.2 | LLM Dev | Additional template slides; wire content keys
4.6.3 | LLM Dev | Assemble full 10-slide deck; verify order and footers
4.7 | Deployment | Performance & robustness | 17-Sep-2026 | 23-Sep-2026
4.7.1 | Deployment | Concurrent generation (thread pool) for overviews, CPI, prior-review; retrieve context once
4.7.2 | Deployment | Fail-soft everywhere (network/parse); ephemeral CPI download (no persistence)
4.7.3 | Deployment | Idempotent index checks; full ingest first run, --skip-ingest on reruns
4.8 | Monitoring | API status mapping & docs | 17-Sep-2026 | 23-Sep-2026
4.8.1 | Monitoring | Status label -> code mapping for Risk Analysis / Scoping AI / Scoping Deck APIs
4.8.2 | Monitoring | Emission hooks (state QUEUED/RUNNING/COMPLETED/FAILED, progress i/N)
4.8.3 | Monitoring | Documentation + run instructions for the scoping deck
Sprint 5: FastAPI Layer & API Hardening -- 24-Sep-2026 to 30-Sep-2026
5.1 | Deployment | FastAPI application setup -- app factory, lifespan context (LLM + index manager init), CORS, OpenAPI config | 24-Sep-2026 | 30-Sep-2026
5.1.1 | Deployment | Create src/api/app.py: FastAPI factory with lifespan for LLM provider and index manager initialization on startup
5.1.2 | Deployment | Configure CORS middleware, request timeout (120s), OpenAPI title/description/tags matching project branding
5.1.3 | Deployment | Verify app starts locally; /docs endpoint accessible; all registered routes appear in OpenAPI spec
5.2 | Deployment | /audit POST endpoint -- async pipeline trigger, background task, immediate job_id response (202 Accepted) | 24-Sep-2026 | 30-Sep-2026
5.2.1 | Deployment | Implement POST /audit: accept AuditRequest; trigger supervisor.run() via asyncio background task; store result by job_id
5.2.2 | Deployment | Return 202 Accepted with job_id immediately; use in-memory dict or asyncio.Queue as job result store
5.2.3 | Deployment | Test with sample audit question: verify 202 response, job_id format, and result stored correctly on completion
5.3 | Deployment | /status and /health endpoints -- poll job result; liveness probe; readiness check (index + LLM connectivity) | 24-Sep-2026 | 30-Sep-2026
5.3.1 | Deployment | GET /status/{job_id}: return {status: pending¦complete¦failed, result: AuditResponse¦null, error: str¦null}
5.3.2 | Deployment | GET /health: liveness probe returns 200 OK; GET /ready: readiness checks index connectivity and LLM ping
5.3.3 | Deployment | Test polling loop end-to-end: POST /audit → poll GET /status → verify complete result returned in response
5.4 | Deployment | AuditRequest and AuditResponse Pydantic schemas -- full field validation, max lengths, type constraints | 24-Sep-2026 | 30-Sep-2026
5.4.1 | Deployment | AuditRequest: question_text (max 2000 chars), response_text (max 5000), auditor_id (matches AUDITOR_ID), questionnaire_type enum validator
5.4.2 | Deployment | AuditResponse: job_id (UUID), status, risk_level (High/Medium/Low/No Risk), scope_identified, rationale, evidence_citations list, timestamp
5.4.3 | Deployment | Test schemas with edge cases: empty strings → 422, oversized inputs → 422, invalid questionnaire_type → 422
5.5 | Deployment | Auth middleware -- X-API-Key header validation; 401 on missing or invalid key; keys from env var | 24-Sep-2026 | 30-Sep-2026
5.5.1 | Deployment | Implement API key middleware: load VALID_API_KEYS from env (comma-separated); validate X-API-Key header on every request
5.5.2 | Deployment | Return 401 Unauthorized with JSON error body on missing or invalid key; skip validation on /health and /ready only
5.5.3 | Deployment | Test with valid key → 200; missing header → 401; wrong key → 401; confirm /health bypasses auth correctly
5.6 | Deployment | Input sanitization and rate limiting -- HTML/injection strip, max lengths enforced, per-IP 10 req/min | 24-Sep-2026 | 30-Sep-2026
5.6.1 | Deployment | Input sanitization: strip HTML tags, reject null bytes and control characters, enforce max length at schema level
5.6.2 | Deployment | Add per-IP rate limiting using slowapi or token-bucket: max 10 requests/minute; return 429 with Retry-After header
5.6.3 | Deployment | Test rate limit: send 11 requests within 60s from same IP; confirm 429 fires on 11th; confirm reset after 60s
5.7 | Deployment | API documentation and OpenAPI spec -- complete endpoint docs, field descriptions, example request/response | 24-Sep-2026 | 30-Sep-2026
5.7.1 | Deployment | Add docstrings and response_model annotations to all 4 endpoints; add Field(description=...) to all schema fields
5.7.2 | Deployment | Export OpenAPI JSON spec via /openapi.json; review completeness: all fields documented, examples present
5.7.3 | Deployment | Share spec with team for review; update endpoint naming or response structure based on feedback
5.8 | LLM Dev | Post-demo prompt refinement -- incorporate Sep 9 feedback; fix edge cases; regression test 20 questions | 24-Sep-2026 | 30-Sep-2026
5.8.1 | LLM Dev | Collect all Sep 9 demo feedback: scope misroutes, hallucinated citations, formatting gaps, missing evidence references
5.8.2 | LLM Dev | Apply targeted prompt improvements; update guardrails G1-G10 for newly observed failure modes
5.8.3 | LLM Dev | Run regression test on 20 representative questions across 5 scope areas; confirm no regressions from prompt changes
Sprint 6: Deployment, Scope Expansion & Benchmarking -- 01-Oct-2026 to 05-Oct-2026
6.1 | Deployment | Databricks job configuration -- cluster YAML, job parameters, Unity Catalog permissions, volume mount verification | 01-Oct-2026 | 05-Oct-2026
6.1.1 | Deployment | Configure Databricks job: cluster policy, runtime version, libraries from requirements.txt, AUDITOR_ID as job parameter
6.1.2 | Deployment | Grant Unity Catalog permissions on all 4 vector indexes, 4 volume paths, and transactional Delta tables
6.1.3 | Deployment | Trigger test job run via Databricks REST API; verify successful end-to-end pipeline execution in job logs
6.2 | Deployment | Docker containerization -- finalize Dockerfile, docker-compose, container health check, end-to-end container test | 01-Oct-2026 | 05-Oct-2026
6.2.1 | Deployment | Finalize multi-stage Dockerfile: optimize layer caching, pin all dependency versions, set non-root user (uid 1000)
6.2.2 | Deployment | Write docker-compose.yml: bind-mount .env file, expose FastAPI port 8000, Docker health check on GET /health
6.2.3 | Deployment | Full container test: docker build + docker run with all env vars; verify main.py and FastAPI /audit both complete successfully
6.3 | Deployment | CI/CD pipeline -- GitHub Actions: syntax check, Docker build, image push to Azure Container Registry on release tag | 01-Oct-2026 | 05-Oct-2026
6.3.1 | Deployment | GitHub Actions workflow: trigger on push to main; run py_compile on all src/ files; fail build on any syntax error
6.3.2 | Deployment | Add job: Docker build on every push; push image to Azure Container Registry on git tag matching v*.*.*
6.3.3 | Deployment | Test full CI/CD pipeline end-to-end; verify build passes, image appears in ACR, and tagged release triggers push
6.4 | Monitoring | Structured logging and alerting -- JSON log schema, error rate alerting, Databricks log aggregation via Delta Lake | 01-Oct-2026 | 05-Oct-2026
6.4.1 | Monitoring | Standardize log format: JSON structured logs with fields agent_name, question_id, scope, confidence, latency_ms, status
6.4.2 | Monitoring | Aggregate logs to Delta Lake table; configure alert rule: error_rate > 5% per 100 questions → notify via email/Teams
6.4.3 | Monitoring | Test alert: force 6 errors in 100 requests; confirm alert fires within 5 min; verify logs are queryable in Delta table
6.5 | Data Prep | Scope area 2-9 policy document collation -- identify, download and stage all policy docs for 8 additional scope areas | 01-Oct-2026 | 05-Oct-2026
6.5.1 | Data Prep | Identify scope-specific policy documents (SOPs, guidelines, CPR sections) for 8 additional FCPA scope areas
6.5.2 | Data Prep | Upload documents to correct Databricks Volume paths under policy_volume and auditors_supporting_documents
6.5.3 | Data Prep | Verify file counts, formats and auditor subfolder structure; confirm fcpa_scope_policy_index already covers all 48 via CPR Excel
6.6 | Data Prep | Ingest scope 2-9 documents -- tpi_due_diligence_index and auditor_supporting_docs_index updated with new scope content | 01-Oct-2026 | 05-Oct-2026
6.6.1 | Data Prep | Run ingestion pipeline for scope 2-9 policy docs: load → chunk (800 tokens, 100 overlap) → embed → upsert to tpi_due_diligence_index
6.6.2 | Data Prep | Run supporting docs ingestion for all auditor folders covering scope areas 2-9; verify auditor_folder tag on all new chunks
6.6.3 | Data Prep | Run scope-filtered retrieval queries for each new scope area; confirm relevant chunks surface in top-5 results
6.7 | ML Dev | Offline retrieval evaluation -- precision@5 and recall@5 across all 4 indexes; tune parameters for low-performing scopes | 01-Oct-2026 | 05-Oct-2026
6.7.1 | ML Dev | Build evaluation dataset: 10 queries per scope area with known-relevant chunk IDs for all 9 scope areas
6.7.2 | ML Dev | Run retrieval_evaluator.py: precision@5 and recall@5 per index; log results to Delta table; flag any index < 0.70 precision
6.7.3 | ML Dev | Tune top_k or MQR n_alternatives for underperforming scope areas; re-evaluate and document final metric scores
6.8 | LLM Dev | Async performance benchmarking -- Phase-level latency profiling; bottleneck identification; optimization report | 01-Oct-2026 | 05-Oct-2026
6.8.1 | LLM Dev | Profile end-to-end pipeline: measure Phase 0 (scope ID), Phase A (parallel retrieval), Phase B (sequential) latency per question
6.8.2 | LLM Dev | Compare aretrieve() vs sync retrieve() timing; measure MQR LLM call overhead vs quality gain; identify worst-performing agent node
6.8.3 | LLM Dev | Implement targeted optimizations for identified bottlenecks; document final latency numbers for stakeholder reporting

## Sprint 1
Sprint 1: Pipeline Core & Ingestion
Goal: Complete the 8-agent LangGraph pipeline: all 4 vector indexes, multi-auditor supporting docs, AUDITOR_ID env routing, fcpa_scope_policy_index (96 chunks), universal guardrails and Dockerfile ¦ Start: 27-Aug-2026 End: 02-Sep-2026
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
1.1 | Data Prep | Settings, index names & AUDITOR_ID env routing -- remove hardcoded auditor; fresh v2 index names
1.1.1 | Data Prep | Remove current_auditor_folder from settings.py; read AUDITOR_ID from env at startup; raise clear error if missing
1.1.2 | Data Prep | Update all 4 index names to v2: hcbi_policy_index, tpi_due_diligence_index, auditor_supporting_docs_index, fcpa_scope_policy_index
1.1.3 | Data Prep | Validate settings load from .env locally and from Databricks secret scope; confirm AUDITOR_ID flows to EvidenceRetrievalTool
1.2 | Data Prep | Vector index manager -- auditor_folder column; is_populated_any(); schema v2 for all 4 indexes
1.2.1 | Data Prep | Add auditor_folder: string column to all 4 index schemas in ensure_index(); update upsert_chunks() to write auditor_folder field
1.2.2 | Data Prep | Implement is_populated_any(index_key): epsilon-vector probe without scope_id filter for supporting and scope_policy indexes
1.2.3 | Data Prep | Update result parsing: auditor_folder at column 13; similarity_score at column 14; handle len(row) guards
1.3 | Data Prep | Multi-auditor supporting docs ingestion -- per-subfolder tagging with auditor_folder; all auditors in one index
1.3.1 | Data Prep | _ensure_supporting_docs_index(): iterate auditor subfolders (Sam_1, Kaitlyn_1, Naeem_1 ...) under auditors_supporting_documents volume
1.3.2 | Data Prep | Tag every chunk via model_copy(update={'auditor_folder': folder_name}); log per-folder doc and chunk counts
1.3.3 | Data Prep | Validate index populated for all auditor folders; run filtered query per auditor; confirm isolation between folders
1.4 | Data Prep | fcpa_scope_policy_index -- CPRScopeExtractor producing 96 chunks (risk_profile + audit_guidance per scope area)
1.4.1 | Data Prep | Build CPRScopeExtractor: 48-sheet-to-scope-ID mapping; extract cols C+D+E+P (risk_profile) and F+O (audit_guidance) per sheet; skip 3 header rows
1.4.2 | Data Prep | _ensure_scope_policy_index(): download CPR Excel from volume, extract chunks, batch upsert to fcpa_scope_policy_index
1.4.3 | Data Prep | Validate 96 chunks indexed (48 scope areas x 2 chunk types); run sample scope-filtered queries; confirm top-2 retrieval precision
1.5 | LLM Dev | 8-agent LangGraph pipeline -- Phase 0 scope routing → Phase A parallel retrieval → Phase B sequential analysis
1.5.1 | LLM Dev | Phase 0: ScopeIdentifierAgent with 48 FCPA scope areas, 4-line output format (Primary, Additional, Reasoning, Confidence)
1.5.2 | LLM Dev | Phase A: asyncio.gather(HcbiPolicyAgent, PolicyKnowledgeAgent, SupportingDocsAgent) -- fully parallel, non-blocking
1.5.3 | LLM Dev | Phase B: RiskEvaluationAgent → TransactionalDataAgent (conditional) → RiskClassifierAgent → RiskWriterAgent -- sequential
1.6 | LLM Dev | PolicyKnowledgeAgent dual-tool routing -- retrieve_scope_area_policy always; retrieve_due_diligence_policy for DUE_DILIGENCE scope only
1.6.1 | LLM Dev | Tool 1: retrieve_scope_area_policy(query, scope_id) → ScopePolicyRetrievalTool (fcpa_scope_policy_index, top_k=2)
1.6.2 | LLM Dev | Tool 2: retrieve_due_diligence_policy(query) → PolicyRetrievalTool (tpi_due_diligence_index), called ONLY when scope = DUE_DILIGENCE
1.6.3 | LLM Dev | Update policy_knowledge_prompt: document both tools, routing rule, dual output format (SCOPE AREA POLICY + DUE DILIGENCE POLICY sections)
1.7 | LLM Dev | Universal guardrails on all 8 agent prompts -- G1-G10 covering hallucination, bias, format, scope and confidence
1.7.1 | LLM Dev | Implement guardrails.py: UNIVERSAL block G1-G6 (no hallucination, no invented data, FCPA only, no advice, no PII, no bias)
1.7.2 | LLM Dev | Add scope-specific guardrails: G7 (valid scope IDs only), G8 (exact 4-line format), G9 (no risk assessment in scope agent), G10 (confidence calibration)
1.7.3 | LLM Dev | Apply guardrail block to all 8 agent system prompts; run py_compile on all prompt files; verify guardrail text in each compiled prompt
1.8 | Deployment | Dockerfile + README + runner entry points -- main.py ingestion + all phases; resume_from_idr.py IDR resume
1.8.1 | Deployment | Multi-stage Dockerfile: Python 3.11 slim base, requirements.txt install, src/ copy, AUDITOR_ID + Azure/Databricks env vars, non-root user
1.8.2 | Deployment | README: architecture diagram, setup steps, .env template, how to run ingestion vs full audit, AUDITOR_ID usage, Databricks job setup
1.8.3 | Deployment | Validate both main.py and resume_from_idr.py read AUDITOR_ID from env; raise RuntimeError with clear message if missing; output filename includes auditor ID
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 2
Sprint 2: Retrieval Intelligence & Demo Preparation
Goal: BM25Reranker + MQR hybrid retrieval on all tools; async aretrieve() everywhere; ScopeIdentifier confidence threshold (0.70) + retry; end-to-end simulation for 9 scope areas; retrieval evaluation; internal demo rehearsal ¦ Start: 03-Sep-2026 End: 09-Sep-2026
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
2.1 | LLM Dev | BM25Reranker -- BM25Okapi RRF fusion on EvidenceRetrievalTool; top_k*4 candidate pool
2.1.1 | LLM Dev | Build BM25Reranker using rank-bm25: BM25Okapi corpus, RRF score = 1/(60+sem_rank) + 1/(60+bm25_rank); return top_k by RRF
2.1.2 | LLM Dev | Wire into EvidenceRetrievalTool.retrieve(): fetch candidate_k = top_k*4 from semantic search; BM25 rerank candidate pool to top_k
2.1.3 | LLM Dev | Validate on 15 evidence queries with specific document names (e.g. Starters_Leavers_Report_Q3.pdf); confirm BM25 corrects semantic ranking misses
2.2 | LLM Dev | MultiQueryRetriever extension -- MQR on HCBI (n=2), Policy (n=2), Evidence (n=3); deduplication by similarity_score
2.2.1 | LLM Dev | Extend MQR to HcbiRetrievalTool (n=2) and PolicyRetrievalTool (n=2); EvidenceRetrievalTool already uses n=3
2.2.2 | LLM Dev | MQR deduplication: keep highest similarity_score per chunk_id across all query variants before returning top_k
2.2.3 | LLM Dev | Validate MQR improves recall@5 on 20 test queries across HCBI and Policy indexes; confirm no duplicate chunks in result
2.3 | LLM Dev | Async retrieval pipeline -- aretrieve() on all 4 tools; MQR async with asyncio.gather; Phase A fully non-blocking
2.3.1 | LLM Dev | MQR.aretrieve(): generate alternatives via LLM.ainvoke(); run all searches in parallel via asyncio.gather + asyncio.to_thread
2.3.2 | LLM Dev | Add aretrieve() to HcbiRetrievalTool, PolicyRetrievalTool, ScopePolicyRetrievalTool; EvidenceRetrievalTool adds aretrieve_targeted()
2.3.3 | LLM Dev | Benchmark Phase A: compare wall-clock latency sync vs async for parallel hcbi+policy+supporting retrieval on 10 sample questions
2.4 | LLM Dev | ScopeIdentifier confidence threshold & retry -- confidence < 0.70 fallback to DUE_DILIGENCE; retry once on empty result
2.4.1 | LLM Dev | Update scope_identifier_prompt: add G10 confidence calibration rule (high >= 0.85 / moderate 0.70-0.84 / low < 0.70); add Confidence line to OUTPUT FORMAT
2.4.2 | LLM Dev | Update supervisor._run_scope_identification(): parse confidence from 4th output line; retry once if no scopes returned; fall back to DUE_DILIGENCE if confidence < 0.70
2.4.3 | LLM Dev | Validate on 10 ambiguous questions: confirm DUE_DILIGENCE fallback triggers correctly; log confidence scores and retry events
2.5 | LLM Dev | Demo data preparation -- Planning + IDR questionnaire for 9 demo scope areas; all indexes verified populated
2.5.1 | LLM Dev | Set AUDITOR_ID env var for demo auditor; confirm all 4 indexes populated (run is_populated checks); load questionnaire rows for 9 scope areas
2.5.2 | LLM Dev | Run python main.py end-to-end; monitor Phase 0 scope routing for all 9 scopes; capture output Excel
2.5.3 | LLM Dev | Review all output rows: verify scope routing accuracy, risk classifications, HCBI citations and evidence document references
2.6 | LLM Dev | Simulation review and prompt tuning -- fix scope misroutes and risk writer gaps identified in demo run
2.6.1 | LLM Dev | Analyze simulation output: catalog scope misroutes, low-confidence assignments, hallucinated citations, weak rationale
2.6.2 | LLM Dev | Apply targeted prompt fixes to scope_identifier_prompt and risk_writer_prompt; add guardrails for newly observed failure modes
2.6.3 | LLM Dev | Re-run simulation on corrected pipeline; confirm improvement on previously failing questions; no regressions on passing ones
2.7 | ML Dev | Retrieval evaluation -- precision@k and recall@k across all 4 indexes using retrieval_evaluator.py
2.7.1 | ML Dev | Build evaluation dataset: 10 queries per scope area with known-relevant chunk IDs for all 9 demo scopes
2.7.2 | ML Dev | Run precision@5 and recall@5 per index; tune top_k_hcbi, top_k_policy, top_k_supporting if below 0.70 precision
2.7.3 | ML Dev | Document final retrieval parameters and evaluation scores; include in demo reference pack
2.8 | Documentation | Demo script, rehearsal and stakeholder narrative -- dry-run all 9 scopes; one-pager for stakeholders
2.8.1 | Documentation | Write demo script: auditor ID, 9 scope areas, key questions to highlight, expected risk findings and evidence citations
2.8.2 | Documentation | Full pipeline dry-run: time end-to-end for all 9 scopes; target < 4 min per question; fix any last-minute issues
2.8.3 | Documentation | Prepare stakeholder one-pager: 8-agent architecture overview, what the AI does, how scope routing works, sample output row
*** DEMO MILESTONE: 09 Sep 2026 -- Internal Demo, 9 Scope Areas ***
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 3
Sprint 3: AI Scope & Scoping Deck Automation
Goal: AI Scope module (Output C -> per-scope Overall Risk Category from avg Likelihood x Impact, proposed sample size from CPR guidance, AI risk summary); Scoping Deck foundation -- questionnaire + supporting-docs ingestion (questionnaire_index); config-driven python-pptx renderer with J&J brand fonts / footer / locked logo; Slide 1 (Opening) and Slide 2 (Market Overview + live CPI) ¦ Start: 10-Sep-2026 End: 16-Sep-2026
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
3.1 | Data Prep | AI Scope Output C loader -- Excel 3rd sheet / Delta table source config
3.1.1 | Data Prep | Source config (EXCEL ¦ DB_TABLE) via env; resolve Output C from workbook 3rd sheet or Delta table
3.1.2 | Data Prep | Normalize headers to internal keys (Scope Area, Risk Type, Likelihood, Impact, Risk Description)
3.1.3 | Data Prep | Load rows into typed objects; validate required columns present; log row count
3.2 | ML Dev | Overall Risk Category & proposed sample size (deterministic)
3.2.1 | ML Dev | Group Output C by scope area; score = Likelihood x Impact per risk; average across the scope
3.2.2 | ML Dev | Map averaged score to band (>=15 High, >=10 Medium, else Low); blank when no L/I present
3.2.3 | ML Dev | Fetch proposed sample size from CPR guidance workbook (col K) per scope; no buffer; volume download
3.3 | LLM Dev | AI Scope risk summary + Excel output
3.3.1 | LLM Dev | Per-scope LLM summary (bullets) of risk descriptions; note past-audit/SI/Legal similarity if present
3.3.2 | LLM Dev | Write AI Scope Excel: Scope Area, Overall Risk Category, Proposed Sample Size, Summary of Risks
3.3.3 | LLM Dev | Validate against a sample audit; run end-to-end for Sam_1
3.4 | Data Prep | Scoping Deck questionnaire ingestion (slide_1)
3.4.1 | Data Prep | QuestionnaireIndexManager: create questionnaire_index; push IDR + Planning Q&A with metadata
3.4.2 | Data Prep | Ensure auditor supporting docs in shared auditor_supporting_docs_index (reuse pipeline helper)
3.4.3 | Data Prep | Idempotent checks (skip if populated per auditor); retrieval sanity check
3.5 | Deployment | Config-driven python-pptx deck renderer
3.5.1 | Deployment | DeckSpec (SlideSpec / FieldSpec / FieldKind) + DeckRenderer; 16:9 blank layout
3.5.2 | Deployment | J&J brand fonts (Johnson Display Headings / Johnson Text Body) applied per field spec
3.5.3 | Deployment | Bulleted body with **bold** markup, justified spacing; multi-line text fields
3.6 | Deployment | Common footer + locked logo
3.6.1 | Deployment | Footer on every slide: J&J logo, Attorney-Client Privilege, Global Audit & Assurance, page number
3.6.2 | Deployment | Insert JNJ shorthand logo (fixed 0.45 x 0.19in) and lock (noMove / noResize / noSelect)
3.6.3 | Deployment | Fonts/colours per spec (#EB1700 header, #564C47 footer); verify render
3.7 | LLM Dev | Slide 1 Opening + Slide 2 Market Overview generator
3.7.1 | LLM Dev | Opening slide: <Entity> <MRC> Compliance Process Review (2-line), review period, current date
3.7.2 | LLM Dev | Market context retriever (questionnaire + supporting docs) + reference library (prior overviews)
3.7.3 | LLM Dev | Market Overview generator (SAM only, 8-10 bullets, grounded, reference-styled)
3.8 | LLM Dev | CPI live integration (Slide 2)
3.8.1 | LLM Dev | Resolve TI data file URL from CPI page HTML; download xlsx in-memory (ephemeral); namespace-fix parse
3.8.2 | LLM Dev | Read country by ISO3 from timeseries; two most recent years; more/less-corrupt rule; dynamic year
3.8.3 | LLM Dev | Corporate SSL handling (OS trust store / CA bundle / override); merge CPI under Market Overview (8pt gap)
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 4
Sprint 4: Scoping Deck Content Slides & Hardening
Goal: Business Overview (6-section table); Prior CPR & Prior GACS from Output E (past_review_gacs_and_cpr_index, CPR/GACS classification, thematic condensing, dynamic tables); remaining slides toward the 10-slide deck; performance (concurrency, retrieve-once) and robustness (fail-soft, corporate-SSL CPI); API status label mapping ¦ Start: 17-Sep-2026 End: 23-Sep-2026
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
4.1 | LLM Dev | Slide 3 Business Overview -- 6-section generator
4.1.1 | LLM Dev | One structured LLM call -> 6 sections (Overview, Changes, Go-to-Market, Interactions, TPI, Regulations)
4.1.2 | LLM Dev | Ground in IDR + questionnaire + supporting docs; reference-styled from prior Business Overview slides
4.1.3 | LLM Dev | Cap section length (2-4 bullets) to fit; bold key terms
4.2 | Deployment | Business Overview table rendering
4.2.1 | Deployment | TableField + renderer: merged red header (Business Summary - <Entity>), six topic rows
4.2.2 | Deployment | Topic cell (bold 12) + content cell (11) with bullets; cell borders/fills
4.2.3 | Deployment | Fit within one slide; fonts per spec
4.3 | Data Prep | Output E ingestion -> past_review_gacs_and_cpr_index
4.3.1 | Data Prep | Output E loader (Excel/DB); classify each observation CPR vs GACS by report terms (CPR/MAP; GACS)
4.3.2 | Data Prep | PastReviewIndexManager: create index; upsert metadata (scope, description, criticality, year, kind)
4.3.3 | Data Prep | Idempotent ingest (skip if populated per auditor)
4.4 | LLM Dev | Prior CPR & GACS builder
4.4.1 | LLM Dev | Fetch all observations by kind; top-level scope grouping (e.g. 'FFS - X' -> 'FFS')
4.4.2 | LLM Dev | Thematic condense to adaptive 2-3 bullets per scope (one LLM call per slide); keep criticality
4.4.3 | LLM Dev | Report year from chunks; fail-soft fallback to first findings
4.5 | Deployment | Prior CPR / GACS slides (7-8) -- dynamic tables
4.5.1 | Deployment | DynamicTableField + renderer; header 'Findings from previous CPR / GACS <Year>'
4.5.2 | Deployment | Skip-empty slide when no findings; sequential page numbering
4.5.3 | Deployment | Validate one-page fit for both
4.6 | LLM Dev | Remaining slides toward the 10-slide deck
4.6.1 | LLM Dev | Areas in Scope - Proposed (table sourced from AI Scope output)
4.6.2 | LLM Dev | Additional template slides; wire content keys
4.6.3 | LLM Dev | Assemble full 10-slide deck; verify order and footers
4.7 | Deployment | Performance & robustness
4.7.1 | Deployment | Concurrent generation (thread pool) for overviews, CPI, prior-review; retrieve context once
4.7.2 | Deployment | Fail-soft everywhere (network/parse); ephemeral CPI download (no persistence)
4.7.3 | Deployment | Idempotent index checks; full ingest first run, --skip-ingest on reruns
4.8 | Monitoring | API status mapping & docs
4.8.1 | Monitoring | Status label -> code mapping for Risk Analysis / Scoping AI / Scoping Deck APIs
4.8.2 | Monitoring | Emission hooks (state QUEUED/RUNNING/COMPLETED/FAILED, progress i/N)
4.8.3 | Monitoring | Documentation + run instructions for the scoping deck
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 5
Sprint 5: FastAPI Layer & API Hardening
Goal: Build production-ready FastAPI serving layer: /audit, /status, /health endpoints; AuditRequest/AuditResponse schemas; X-API-Key auth middleware; input sanitization; rate limiting; OpenAPI spec; post-demo prompt refinement ¦ Start: 24-Sep-2026 End: 30-Sep-2026
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
5.1 | Deployment | FastAPI application setup -- app factory, lifespan context (LLM + index manager init), CORS, OpenAPI config
5.1.1 | Deployment | Create src/api/app.py: FastAPI factory with lifespan for LLM provider and index manager initialization on startup
5.1.2 | Deployment | Configure CORS middleware, request timeout (120s), OpenAPI title/description/tags matching project branding
5.1.3 | Deployment | Verify app starts locally; /docs endpoint accessible; all registered routes appear in OpenAPI spec
5.2 | Deployment | /audit POST endpoint -- async pipeline trigger, background task, immediate job_id response (202 Accepted)
5.2.1 | Deployment | Implement POST /audit: accept AuditRequest; trigger supervisor.run() via asyncio background task; store result by job_id
5.2.2 | Deployment | Return 202 Accepted with job_id immediately; use in-memory dict or asyncio.Queue as job result store
5.2.3 | Deployment | Test with sample audit question: verify 202 response, job_id format, and result stored correctly on completion
5.3 | Deployment | /status and /health endpoints -- poll job result; liveness probe; readiness check (index + LLM connectivity)
5.3.1 | Deployment | GET /status/{job_id}: return {status: pending¦complete¦failed, result: AuditResponse¦null, error: str¦null}
5.3.2 | Deployment | GET /health: liveness probe returns 200 OK; GET /ready: readiness checks index connectivity and LLM ping
5.3.3 | Deployment | Test polling loop end-to-end: POST /audit → poll GET /status → verify complete result returned in response
5.4 | Deployment | AuditRequest and AuditResponse Pydantic schemas -- full field validation, max lengths, type constraints
5.4.1 | Deployment | AuditRequest: question_text (max 2000 chars), response_text (max 5000), auditor_id (matches AUDITOR_ID), questionnaire_type enum validator
5.4.2 | Deployment | AuditResponse: job_id (UUID), status, risk_level (High/Medium/Low/No Risk), scope_identified, rationale, evidence_citations list, timestamp
5.4.3 | Deployment | Test schemas with edge cases: empty strings → 422, oversized inputs → 422, invalid questionnaire_type → 422
5.5 | Deployment | Auth middleware -- X-API-Key header validation; 401 on missing or invalid key; keys from env var
5.5.1 | Deployment | Implement API key middleware: load VALID_API_KEYS from env (comma-separated); validate X-API-Key header on every request
5.5.2 | Deployment | Return 401 Unauthorized with JSON error body on missing or invalid key; skip validation on /health and /ready only
5.5.3 | Deployment | Test with valid key → 200; missing header → 401; wrong key → 401; confirm /health bypasses auth correctly
5.6 | Deployment | Input sanitization and rate limiting -- HTML/injection strip, max lengths enforced, per-IP 10 req/min
5.6.1 | Deployment | Input sanitization: strip HTML tags, reject null bytes and control characters, enforce max length at schema level
5.6.2 | Deployment | Add per-IP rate limiting using slowapi or token-bucket: max 10 requests/minute; return 429 with Retry-After header
5.6.3 | Deployment | Test rate limit: send 11 requests within 60s from same IP; confirm 429 fires on 11th; confirm reset after 60s
5.7 | Deployment | API documentation and OpenAPI spec -- complete endpoint docs, field descriptions, example request/response
5.7.1 | Deployment | Add docstrings and response_model annotations to all 4 endpoints; add Field(description=...) to all schema fields
5.7.2 | Deployment | Export OpenAPI JSON spec via /openapi.json; review completeness: all fields documented, examples present
5.7.3 | Deployment | Share spec with team for review; update endpoint naming or response structure based on feedback
5.8 | LLM Dev | Post-demo prompt refinement -- incorporate Sep 9 feedback; fix edge cases; regression test 20 questions
5.8.1 | LLM Dev | Collect all Sep 9 demo feedback: scope misroutes, hallucinated citations, formatting gaps, missing evidence references
5.8.2 | LLM Dev | Apply targeted prompt improvements; update guardrails G1-G10 for newly observed failure modes
5.8.3 | LLM Dev | Run regression test on 20 representative questions across 5 scope areas; confirm no regressions from prompt changes
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation

## Sprint 6
Sprint 6: Deployment, Scope Expansion & Benchmarking
Goal: Databricks production job configuration; Docker containerization; CI/CD via GitHub Actions; structured logging and alerting; ingest scope areas 2-9; offline retrieval evaluation (precision@k, recall@k); async performance benchmarking ¦ Start: 01-Oct-2026 End: 05-Oct-2026
Task Ref | Category | Task | Actual Start | Actual End | % Complete | Status | Assigned To | Reviewer
6.1 | Deployment | Databricks job configuration -- cluster YAML, job parameters, Unity Catalog permissions, volume mount verification
6.1.1 | Deployment | Configure Databricks job: cluster policy, runtime version, libraries from requirements.txt, AUDITOR_ID as job parameter
6.1.2 | Deployment | Grant Unity Catalog permissions on all 4 vector indexes, 4 volume paths, and transactional Delta tables
6.1.3 | Deployment | Trigger test job run via Databricks REST API; verify successful end-to-end pipeline execution in job logs
6.2 | Deployment | Docker containerization -- finalize Dockerfile, docker-compose, container health check, end-to-end container test
6.2.1 | Deployment | Finalize multi-stage Dockerfile: optimize layer caching, pin all dependency versions, set non-root user (uid 1000)
6.2.2 | Deployment | Write docker-compose.yml: bind-mount .env file, expose FastAPI port 8000, Docker health check on GET /health
6.2.3 | Deployment | Full container test: docker build + docker run with all env vars; verify main.py and FastAPI /audit both complete successfully
6.3 | Deployment | CI/CD pipeline -- GitHub Actions: syntax check, Docker build, image push to Azure Container Registry on release tag
6.3.1 | Deployment | GitHub Actions workflow: trigger on push to main; run py_compile on all src/ files; fail build on any syntax error
6.3.2 | Deployment | Add job: Docker build on every push; push image to Azure Container Registry on git tag matching v*.*.*
6.3.3 | Deployment | Test full CI/CD pipeline end-to-end; verify build passes, image appears in ACR, and tagged release triggers push
6.4 | Monitoring | Structured logging and alerting -- JSON log schema, error rate alerting, Databricks log aggregation via Delta Lake
6.4.1 | Monitoring | Standardize log format: JSON structured logs with fields agent_name, question_id, scope, confidence, latency_ms, status
6.4.2 | Monitoring | Aggregate logs to Delta Lake table; configure alert rule: error_rate > 5% per 100 questions → notify via email/Teams
6.4.3 | Monitoring | Test alert: force 6 errors in 100 requests; confirm alert fires within 5 min; verify logs are queryable in Delta table
6.5 | Data Prep | Scope area 2-9 policy document collation -- identify, download and stage all policy docs for 8 additional scope areas
6.5.1 | Data Prep | Identify scope-specific policy documents (SOPs, guidelines, CPR sections) for 8 additional FCPA scope areas
6.5.2 | Data Prep | Upload documents to correct Databricks Volume paths under policy_volume and auditors_supporting_documents
6.5.3 | Data Prep | Verify file counts, formats and auditor subfolder structure; confirm fcpa_scope_policy_index already covers all 48 via CPR Excel
6.6 | Data Prep | Ingest scope 2-9 documents -- tpi_due_diligence_index and auditor_supporting_docs_index updated with new scope content
6.6.1 | Data Prep | Run ingestion pipeline for scope 2-9 policy docs: load → chunk (800 tokens, 100 overlap) → embed → upsert to tpi_due_diligence_index
6.6.2 | Data Prep | Run supporting docs ingestion for all auditor folders covering scope areas 2-9; verify auditor_folder tag on all new chunks
6.6.3 | Data Prep | Run scope-filtered retrieval queries for each new scope area; confirm relevant chunks surface in top-5 results
6.7 | ML Dev | Offline retrieval evaluation -- precision@5 and recall@5 across all 4 indexes; tune parameters for low-performing scopes
6.7.1 | ML Dev | Build evaluation dataset: 10 queries per scope area with known-relevant chunk IDs for all 9 scope areas
6.7.2 | ML Dev | Run retrieval_evaluator.py: precision@5 and recall@5 per index; log results to Delta table; flag any index < 0.70 precision
6.7.3 | ML Dev | Tune top_k or MQR n_alternatives for underperforming scope areas; re-evaluate and document final metric scores
6.8 | LLM Dev | Async performance benchmarking -- Phase-level latency profiling; bottleneck identification; optimization report
6.8.1 | LLM Dev | Profile end-to-end pipeline: measure Phase 0 (scope ID), Phase A (parallel retrieval), Phase B (sequential) latency per question
6.8.2 | LLM Dev | Compare aretrieve() vs sync retrieve() timing; measure MQR LLM call overhead vs quality gain; identify worst-performing agent node
6.8.3 | LLM Dev | Implement targeted optimizations for identified bottlenecks; document final latency numbers for stakeholder reporting
Category Legend: | Policy & Use Case | Data Prep | LLM Dev | ML Dev | Monitoring | Deployment | Documentation